| Lighthief Cyprus Ltd | LETTER OF INTENT Ref: LCY-LOI-ESP-PIPELINE-2026-R7 Date: May 2026 STRICTLY CONFIDENTIAL |
| --- | --- |

Letter of Intent

Esperia Energy Group — BESS Pipeline Commitment (Schedule 1)

PARTIES

| Contractor | Lighthief Cyprus Ltd Registration No. HE 477423 28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus office@lighthief.com ¦ +357 77 77 00 50 (hereinafter "Lighthief" or the "Contractor") |
| --- | --- |
| Client | Esperia Energy Group represented by: Dino Constantinou (Owner) Famagusta, Limassol and Nicosia districts, Cyprus (hereinafter "the Client") |

RECITALS

A.  Lighthief supplies and installs grid-connected BESS for hybrid PV projects in Cyprus.

B.  The Client (Esperia Energy Group) develops BESS projects in Famagusta, Limassol, and Nicosia.

C.  The Client wishes to commit to the nine (9) pipeline parks in Schedule 1 (73.5 MW / 305.0 MWh). Galascope 1 and Galascope 2 are covered under a separate Letter of Intent with Galascope Ltd (Ref: LCY-LOI-GAL-B1-2026).

NOW THEREFORE, the Parties agree as follows:

1.   COMMITMENT AND PURPOSE

1.1  The Client confirms its intention to award BESS EPC contracts to Lighthief for nine (9) parks in Schedule 1 (73.5 MW / 305.0 MWh). Combined indicative value €30,043,928 (excl. VAT), based on Linyang quotation LY202601271 and group-order pricing. This LOI does not include Galascope Ltd parks.

1.2  This LOI supports Lighthief's procurement and OEM planning. Except where expressly stated as binding below, this LOI is not an obligation to sign any EPC; each phase EPC is binding only when signed.

1.3  (Binding) If the Client withdraws from Schedule 1 after Lighthief has reasonably relied on this LOI, the Client shall reimburse documented pre-contractual costs directly incurred for Schedule 1 parks only, unless withdrawal is for a Valid Reason.

Valid Reason means any of the following (with written notice and evidence):

(a) the Client fails to obtain grid Connection Terms / licence for a park within the EPC longstop and elects not to proceed with that park;

(b) a change in law, regulation, or DSO/EAC requirement makes BESS installation at a listed park unlawful or technically impossible, certified by a qualified adviser;

(c) mutual written agreement to terminate this LOI or a park;

(d) Lighthief materially breaches this LOI or an executed EPC and does not remedy within thirty (30) days of notice;

(e) the Client formally removes a park from its development portfolio with thirty (30) days' notice before Lighthief incurs new third-party costs for that park.

Documented pre-contractual costs means third-party costs actually paid or contractually committed (with invoices, contracts, or payment proofs) and directly attributable to Schedule 1 parks, limited to:

EAC / DSO application fees, grid-connection submissions, and related authority charges;

third-party contractors engaged for listed parks (e.g. electrical design, geotechnical or civil studies, planning, environmental or technical reports);

OEM (Linyang) reservation, batch planning, or prepayment deposits invoiced to Lighthief for equipment referable to Schedule 1;

submitted studies and filings ordered before withdrawal (e.g. EIA, grid impact, connection studies) with dated deliverables.

Excluded: Client internal staff time, overhead, financing costs, and any work not linked to a Schedule 1 park. Lighthief shall provide a cost schedule with supporting documents within twenty (20) Business Days of a reimbursement request.

2.   SCHEDULE 1 — PARKS AND INDICATIVE PRICING

Schedule 1 figures are Indicative Prices only. Final terms are set under Section 4 and in each executed EPC (Lighthief template v5.1 or successor).

| 9 Parks Schedule 1 Total | 73.49 MW Total BESS Power | 305.0 MWh Total BESS Energy | €30,043,928 Indicative Value (ex. VAT) |
| --- | --- | --- | --- |

| Park / Project | District | MW | MWh | Indicative Price (ex. VAT) |
| --- | --- | --- | --- | --- |
| Esperia Energy (Famagusta) | Famagusta | 6.50 | 20.0 | €2,316,815 |
| Esperia Green Energy (Limassol) | Limassol | 8.00 | 60.0 | €5,644,044 |
| Esperia Energy (Frenaros) | Famagusta | 25.00 | 100.0 | €10,088,014 |
| Phase 1 — 2026 Delivery (Esperia pipeline) — Subtotal |  | 39.50 | 180.0 | €18,048,873 |
| Esperia Green Energy (Famagusta 2) | Famagusta | 5.00 | 20.0 | €2,189,416 |
| Esperia Energy (Tseri) | Nicosia | 7.20 | 20.0 | €2,382,035 |
| Esperia Energy (Tseri 2-A) | Nicosia | 2.75 | 10.0 | €1,084,620 |
| Esperia Energy (Tseri 2-B) | Nicosia | 7.99 | 30.0 | €2,912,993 |
| Esperia Energy (Tseri 2-C) | Nicosia | 6.30 | 25.0 | €1,551,848 |
| Esperia Energy (Tseri 3) | Nicosia | 4.75 | 20.0 | €1,874,143 |
| Phase 3 — 2028 Delivery (Famagusta 2 + Tseri Portfolio) — Subtotal |  | 33.99 | 125.0 | €11,995,055 |
| TOTAL SCHEDULE 1 (9 pipeline parks) |  | 73.49 | 305.0 | €30,043,928 |

3.   INDICATIVE PROGRAMME

Target dates are indicative; each EPC sets binding milestones.

| Batch / Phase | Parks | MWh | EPC target | Indicative value (ex VAT) |
| --- | --- | --- | --- | --- |
| Phase 1 — 2026 | 3 | 180.0 | Q2 2026 | €18,048,873 |
| Phase 3 — 2028 (Famagusta 2 + Tseri) | 6 | 125.0 | 2028 | €11,995,055 |

4.   COMMERCIAL SUMMARY

4.1  Indicative payment structure for each EPC (detail in the EPC): 30% advance; 55% pre-shipment; 10% on PAC; 5% retention released after a three (3) month defects liability period following PAC.

4.2  Prices exclude VAT. Client scope includes civil works, planning, permits, and grid connection fees unless agreed otherwise in the EPC.

4.3  (Pricing basis — two-way, single source) Contract Price for each park is expressed per effective MWh (nameplate energy capacity) in that park's EPC Schedule A. Effective MWh for each pipeline park will be stated in that park's phase EPC Schedule A. Schedule 1 Indicative Prices and executed EPC Confirmed Prices use the same pricing source: Linyang Quotation LY202601271 (January 2026). Prices may adjust up or down only via the Confirmed Price mechanism in Section 4.5 (Mysteel lithium and EUR/CNY — no other indices).

4.4  (Indicative Price) Schedule 1 and each EPC Component A and Component B at signing are Indicative Prices from LY202601271, exclusive of VAT. The Indicative Price is binding on Lighthief from the EPC Effective Date until the Confirmed Price Certificate Date (as defined in the EPC).

4.5  (Confirmed Price mechanism — EPC v5.1 §6.1) Each executed EPC shall apply the following (same rules for Indicative and Confirmed Price):

Within fourteen (14) days after the Client receives grid Connection Terms for that park or phase, Lighthief issues a Confirmed Price Certificate fixing the Contract Price for all subsequent payment milestones.

The Confirmed Price equals the Indicative Price adjusted two-way where: (i) the Mysteel lithium carbonate reference (155,000 CNY/tonne (Mysteel China battery-grade spot, January 2026 monthly average)) moves by more than ten percent (10%); and/or (ii) EUR/CNY (8.18 CNY per EUR (January 2026 average)) moves by more than eight percent (8%); and/or (iii) the Client requests a material configuration change in Schedule A. A favourable index movement reduces the Confirmed Price accordingly.

Any net upward adjustment is capped at five percent (5%) of the Indicative Contract Price. If the calculated upward adjustment exceeds 5%, either Party may terminate that EPC without penalty within fourteen (14) days of the Confirmed Price Certificate; advance payments are refunded within thirty (30) days, less reasonable documented costs under Clause 1.3.

Lighthief shall not pass through cost increases caused by Lighthief's own delay or fault.

Advance payment (30%): due within thirty (30) days of the later of EPC Effective Date and Connection Terms (not on signing alone). Connection Terms must be obtained within twelve (12) months of Effective Date (EPC §1A.1 longstop).

Price Basis Certificates: at EPC signing, an Indicative Price Basis Certificate (indices, methodology, effective MWh, Indicative Price); at equipment delivery to Site, a Delivery Price Basis Certificate (Confirmed Price or adjustment shown). Client may dispute within fourteen (14) days of each Certificate.

4.6  Schedule 1 Indicative totals remain valid for ninety (90) days from this LOI. Material changes will be notified at least thirty (30) days before the relevant EPC is signed. Final commercial terms are only those in the executed EPC and Confirmed Price Certificate.

5.   COMPANION AGREEMENTS (INTENT)

5.1  LTSA and EMS: The Client intends to enter LTSA(s) and, where applicable, DISPERON EMS subscription with each commissioned park. Indicative EMS rate EUR 400/MWh/year from PAC (separate addendum).

6.   GOOD FAITH AND PHASE EXIT

6.1  The Parties will negotiate each phase EPC in good faith. If terms are not agreed within sixty (60) days after the relevant EPC target date in Section 3, either Party may end this LOI for that phase only, without liability except Clause 1.3.

7.   EXCLUSIVITY

7.1  (Binding) Until this LOI expires or all Schedule 1 EPCs are signed, and for six (6) months after each park's PAC, the Client shall not, for any Schedule 1 park:

appoint, negotiate with, or execute an EPC or turnkey BESS supply contract with any contractor other than Lighthief Cyprus Ltd; or

procure BESS containers, PCS, MV skids, or integrated BESS equipment from any OEM other than Jiangsu Linyang Energy Storage Technology Co., Ltd (or its authorised distributor for the Cyprus portfolio).

7.2  Exclusivity does not apply if the Client has Valid Reason under Clause 1.3, or if Lighthief fails to execute an EPC for a phase within sixty (60) days after the target date in Section 3 (for that phase only).

7.3  Exclusivity ends immediately if the Client breaches Clause 1.3, 7, or 8 of this LOI, or if Lighthief materially breaches this LOI and does not remedy within thirty (30) days of written notice.

7.4  This exclusivity applies to the nine (9) pipeline parks in Schedule 1 only and does not cover Galascope Ltd parks (separate LOI Ref: LCY-LOI-GAL-B1-2026).

8.   CONFIDENTIALITY

8.1  (Binding) Each Party shall keep confidential this LOI and related information, except to advisers, lenders, or as required by law. Survives five (5) years.

9.   TERM AND GOVERNING LAW

9.1  This LOI runs until the earlier of: all Schedule 1 EPCs signed, thirty-six (36) months from signing, or termination of a phase under Section 6.

9.2  Governed by Cyprus law. Cyprus courts have exclusive jurisdiction.

9.3  Amendments require written agreement.

NATURE OF THIS DOCUMENT: Non-binding except Clauses 1.3, 7, and 8. Covers nine (9) Esperia pipeline parks only. Galascope Ltd batch is under LCY-LOI-GAL-B1-2026 separately. Section 4 summarises the Indicative + Confirmed Price mechanism for each EPC §6.1.

SIGNATURES

IN WITNESS WHEREOF, the authorised representatives of the Parties have executed this Letter of Intent as of the date first written above.

| For and on behalf of Lighthief Cyprus Ltd | For and on behalf of Esperia Energy Group |
| --- | --- |
| Name: Alexander Papacosta | Name: ___________________________ |
| Title: Managing Director | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

Lighthief Cyprus Ltd  |  HE 477423  |  28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus
office@lighthief.com  |  +357 77 77 00 50  |  solarfarms.cy  |  Ref: LCY-LOI-ESP-PIPELINE-2026-R7