| Lighthief Cyprus Ltd | LETTER OF INTENT Ref: LCY-LOI-ESP-PIPELINE-2026-R15 Date: May 2026 STRICTLY CONFIDENTIAL |
| --- | --- |

Letter of Intent

Esperia Energy Group — BESS Pipeline Commitment (Schedule 1)

PARTIES

| Contractor | Lighthief Cyprus Ltd Registration No. HE 477423 28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus office@lighthief.com ¦ +357 77 77 00 50 (hereinafter "Lighthief" or the "Contractor") |
| --- | --- |
| Client | Esperia Energy Group Christaki Kranou 18, Limassol 4046, Cyprus represented by: Ntinos Konstantinos (Owner) (hereinafter "the Client") |

RECITALS

A.  Lighthief supplies and installs grid-connected BESS for hybrid PV projects in Cyprus.

B.  The Client (Esperia Energy Group) develops BESS projects in Famagusta, Limassol, and Nicosia.

C.  The Client wishes to commit to the nine (9) pipeline parks in Schedule 1 (75.5 MW / 315.0 MWh). Galascope 1 and Galascope 2 are covered under a separate Letter of Intent with Galascope Ltd (Ref: LCY-LOI-GAL-B1-2026).

NOW THEREFORE, the Parties agree as follows:

1.   COMMITMENT AND PURPOSE

1.1  The Client confirms its intention to award BESS EPC contracts to Lighthief for nine (9) parks in Schedule 1 (75.5 MW / 315.0 MWh). Combined indicative value €34,458,823 (excl. VAT), based on Linyang quotation LY202601271 and group-order pricing. This LOI does not include Galascope Ltd parks.

1.2  This LOI supports Lighthief's procurement and OEM planning. Except where expressly stated as binding below, this LOI is not an obligation to sign any EPC; each phase EPC is binding only when signed.

1.3  (Binding) If the Client withdraws after Lighthief has relied on this LOI, the Client reimburses third-party costs paid or non-cancellable third-party commitments for Schedule 1 parks (evidenced by invoice or signed contract), unless withdrawal is for a Valid Reason. Total reimbursement under this Clause is capped at €400,000.

Valid Reason: (a) grid Connection Terms / licence not obtained within twelve (12) months of the EPC Effective Date (or such other longstop as the EPC specifies); (b) change in law or DSO/EAC rules makes installation unlawful or impossible (adviser certificate); (c) mutual written termination; (d) Lighthief material breach not remedied within thirty (30) days; (e) project financing for a park is not secured despite reasonable efforts evidenced in writing; (f) Linyang insolvency or sanctions preventing supply. New third-party spend above €50,000 per park requires the Client's prior written approval.

2.   SCHEDULE 1 — PARKS AND INDICATIVE PRICING

| 9 Parks Schedule 1 Total | 75.49 MW Total BESS Power | 315.0 MWh Total BESS Energy | €34,458,823 Indicative Value (ex. VAT) |
| --- | --- | --- | --- |

| Park / Project | District | MW | MWh | Indicative delivery | Licence | Indicative Price (ex. VAT) |
| --- | --- | --- | --- | --- | --- | --- |
| Esperia Energy (Tseri) | Nicosia | 7.20 | 25.0 | 2026 | Licence ~6 months | €3,073,225* |
| Esperia Energy (Tseri 2-A) | Nicosia | 2.75 | 10.0 | Q3 2026 | Fully licensed | €1,206,300* |
| Esperia Energy (Tseri 3) | Nicosia | 4.75 | 20.0 | Q3 2026 | Fully licensed | €2,238,000* |
| Esperia Energy (Famagusta) | Famagusta | 6.50 | 20.0 | Q4 2026 | Per EPC schedule | €2,374,920* |
| Batch 1 — 2026 — Subtotal |  | 21.20 | 75.0 |  |  | €8,892,445 |
| Esperia Green Energy (Limassol) | Limassol | 8.00 | 60.0 | Q2 2027 | Per EPC schedule | €5,644,044 |
| Esperia Energy (Tseri 2-B) | Nicosia | 7.99 | 30.0 | 2027 | ~9 months from licensing | €3,687,870* |
| Esperia Energy (Tseri 2-C) | Nicosia | 6.30 | 25.0 | 2027 | Licence ~6 months | €3,073,225* |
| Batch 2 — 2027 — Subtotal |  | 22.29 | 115.0 |  |  | €12,405,139 |
| Esperia Energy (Frenaros) | Famagusta | 25.00 | 100.0 | Q2 2028 | Per EPC schedule | €10,088,014 |
| Esperia Green Energy (Famagusta 2) | Famagusta | 7.00 | 25.0 | Q2 2028 | Phase 2 | €3,073,225* |
| Batch 3 — 2028 — Subtotal |  | 32.00 | 125.0 |  |  | €13,161,239 |
| TOTAL SCHEDULE 1 (9 pipeline parks) |  | 75.49 | 315.0 |  |  | €34,458,823 |

* Indicative Prices marked * use the nearest Linyang configuration (LY202601271) where MW/MWh is not an exact quoted line: Tseri, Tseri 2-A, Tseri 3, Famagusta, Tseri 2-B, Tseri 2-C, Famagusta 2. Limassol and Frenaros are exact LY lines.

3.   INDICATIVE PROGRAMME

| Batch / Phase | Parks | MWh | EPC target | Indicative value (ex VAT) |
| --- | --- | --- | --- | --- |
| Batch 1 — 2026 | 4 | 75.0 | 2026 (per park) | €8,892,445 |
| Batch 2 — 2027 | 3 | 115.0 | 2027 (per park) | €12,405,139 |
| Batch 3 — 2028 | 2 | 125.0 | Q2 2028 | €13,161,239 |

4.   COMMERCIAL SUMMARY

4.1  Schedule 1 shows Indicative Prices (excl. VAT) from Linyang quotation LY202601271. Payment terms, civil works scope, and the binding Contract Price are fixed in each executed EPC using the Indicative and Confirmed Price mechanism (EPC §6.1).

Effective MWh for each pipeline park will be stated in that park's phase EPC Schedule A.

4.2  Schedule 1 indicatives are valid for ninety (90) days from this LOI for planning. The Confirmed Contract Price for each park or batch is set when Lighthief issues the Confirmed Price Certificate under Clause 4.3.

4.3  (Two-way price commitment) Each EPC will state an Indicative Price (as in Schedule 1 or updated in writing before signing). Within fourteen (14) days after the Client receives grid Connection Terms for that park or batch, Lighthief will issue a Confirmed Price Certificate fixing the Contract Price. The Confirmed Price equals the Indicative Price unless the battery raw-material index (Mysteel lithium carbonate) or EUR/CNY moves beyond the thresholds in EPC §6.1 from the January 2026 reference values (155,000 CNY/tonne (Mysteel China battery-grade spot, January 2026 monthly average); 8.18 CNY per EUR (January 2026 average)). Where a threshold is exceeded, the Confirmed Price adjusts to reflect verified movement on the equipment cost base: downward adjustments are passed through to the Client on milestones not yet invoiced; upward adjustments are capped at five percent (5%) of the Indicative Price. If the calculated upward adjustment would exceed five percent (5%), either Party may decline to proceed with that EPC without penalty. Lighthief will provide a Price Basis Certificate at EPC signing (and at equipment delivery where applicable) showing the reference indices and calculation so the Client can verify how the price follows the market.

4.4  (Price lock — signature by 29 May 2026) The Parties acknowledge that, as of the date of this LOI, the Mysteel lithium carbonate index has moved materially above the January 2026 reference in Clause 4.3, while EUR/CNY remains within the EPC FX threshold. Schedule 1 therefore reflects pricing locked with Linyang on the January 2026 quotation basis, not today's spot index. Linyang has confirmed that where this LOI and the relevant park or batch EPC are executed on or before 29 May 2026, the Indicative Price (as in Schedule 1 or updated in writing before signing) shall be the Confirmed Price for equipment cost purposes, without upward raw-material or FX adjustment for index movement occurring before that EPC Effective Date. Clause 4.3 two-way adjustments apply after signing only to verified movement from the indices stated in the Price Basis Certificate at EPC signing.

5.   NEXT STEPS

5.1  The Parties will negotiate EPCs per batch in Section 3. LTSA, EMS, and warranty terms are agreed in each EPC — not in this LOI.

6.   GOOD FAITH

6.1  The Parties will negotiate each batch EPC in good faith. If terms for a batch are not agreed within ninety (90) days of that batch's EPC target in Section 3, either Party may end this LOI for that batch only, without liability except Clause 1.3.

7.   EXCLUSIVITY

7.1  (Binding) Until this LOI expires or the relevant Schedule 1 EPC is signed, the Client will not appoint another EPC contractor for those parks or procure parallel BESS equipment for them from an OEM other than Linyang (Cyprus portfolio).

7.2  Exclusivity does not apply on Valid Reason (Clause 1.3) or if Lighthief has not proposed an EPC for signature within ninety (90) days of this LOI (unless extended in writing).

7.3  Exclusivity ends when the Schedule 1 EPC is signed, on Valid Reason, or if either Party materially breaches this LOI and does not remedy within thirty (30) days of notice.

7.4  Applies to the nine (9) pipeline parks only — not Galascope Ltd (LCY-LOI-GAL-B1-2026-R15).

8.   CONFIDENTIALITY

8.1  (Binding) Each Party shall keep confidential this LOI and related information, except to advisers, lenders, or as required by law. Survives five (5) years.

9.   TERM AND GOVERNING LAW

9.1  This LOI runs until the earlier of: all Schedule 1 EPCs signed, thirty-six (36) months from signing, or termination of a phase under Section 6.

9.2  Governed by Cyprus law. Cyprus courts have exclusive jurisdiction.

NATURE OF THIS DOCUMENT: Non-binding except Clauses 1.3, 7, and 8. Nine (9) pipeline parks only. Galascope Ltd: LCY-LOI-GAL-B1-2026-R15. Binding price and payment terms are in each EPC.

SIGNATURES

IN WITNESS WHEREOF, the authorised representatives of the Parties have executed this Letter of Intent as of the date first written above.

| For and on behalf of Lighthief Cyprus Ltd | For and on behalf of Esperia Energy Group |
| --- | --- |
| Name: Alexander Papacosta | Name: ___________________________ |
| Title: Managing Director | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

Lighthief Cyprus Ltd  |  HE 477423  |  28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus
office@lighthief.com  |  +357 77 77 00 50  |  solarfarms.cy  |  Ref: LCY-LOI-ESP-PIPELINE-2026-R15