| Lighthief Cyprus Ltd | LETTER OF INTENT Ref: LCY-LOI-GAL-B1-2026-R15 Date: May 2026 STRICTLY CONFIDENTIAL |
| --- | --- |

Letter of Intent

Galascope Ltd — BESS EPC Batch 1 (Galascope 1 + Galascope 2)

PARTIES

| Contractor | Lighthief Cyprus Ltd Registration No. HE 477423 28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus office@lighthief.com ¦ +357 77 77 00 50 (hereinafter "Lighthief" or the "Contractor") |
| --- | --- |
| Client | Galascope Ltd Registration No. HE 303759 Karaiskaki 6, City House, 3032 Limassol, Cyprus represented by: Ntinos Konstantinos (Director) (hereinafter "the Client") |

RECITALS

A.  Lighthief supplies and installs grid-connected BESS for hybrid PV projects in Cyprus.

B.  The Client (Galascope Ltd) is developing two BESS parks at Famagusta (Galascope 1 and Galascope 2) as part of the Esperia Energy Group portfolio.

C.  The Client wishes to proceed with EPC ref. LCY-EPC-GAL-B1-2026 for Galascope 1 (5.0 MW / 20.06 MWh effective) and Galascope 2 (2.5 MW / 10.03 MWh effective), combined indicative value €3,444,300 (excl. VAT).

D.  Other Esperia group pipeline parks are covered under a separate Letter of Intent with Esperia Energy Group (Ref: LCY-LOI-ESP-PIPELINE-2026-R15).

NOW THEREFORE, the Parties agree as follows:

1.   COMMITMENT AND PURPOSE

1.1  The Client confirms its intention to award the BESS EPC contract to Lighthief for two (2) parks in Schedule 1 under LCY-EPC-GAL-B1-2026: Galascope 1 and Galascope 2 (7.50 MW; effective MWh per Schedule A — 20.06 + 10.03). Indicative value €3,444,300 (excl. VAT), confirmed May 2026.

1.2  This LOI supports procurement, OEM planning, and lender review. Except where expressly binding below, obligations arise only when the EPC and companion documents are signed.

1.3  (Binding) If the Client withdraws after Lighthief has relied on this LOI, the Client reimburses third-party costs paid or non-cancellable third-party commitments for Schedule 1 parks (evidenced by invoice or signed contract), unless withdrawal is for a Valid Reason. Total reimbursement under this Clause is capped at €100,000.

Valid Reason: (a) grid Connection Terms / licence not obtained within twelve (12) months of the EPC Effective Date (or such other longstop as the EPC specifies); (b) change in law or DSO/EAC rules makes installation unlawful or impossible (adviser certificate); (c) mutual written termination; (d) Lighthief material breach not remedied within thirty (30) days; (e) project financing for a park is not secured despite reasonable efforts evidenced in writing; (f) Linyang insolvency or sanctions preventing supply. New third-party spend above €50,000 per park requires the Client's prior written approval.

2.   SCHEDULE 1 — PARKS AND INDICATIVE PRICING

| 2 Parks Galascope Batch 1 | 7.50 MW Total BESS Power | 30.09 MWh Total BESS Energy | €3,444,300 Indicative Value (ex. VAT) |
| --- | --- | --- | --- |

| Park | District | MW | MWh (eff.) | Indicative Price (ex. VAT) |
| --- | --- | --- | --- | --- |
| Galascope 1 | Famagusta | 5.00 | 20.06 | €2,238,000 |
| Galascope 2 | Famagusta | 2.50 | 10.03 | €1,206,300 |
| TOTAL — Galascope Batch 1 |  | 7.50 | 30.09 | €3,444,300 |

3.   INDICATIVE PROGRAMME

EPC target: LCY-EPC-GAL-B1-2026 — signing Q2 2026; target PAC 31 January 2027.

4.   COMMERCIAL SUMMARY

4.1  Schedule 1 shows Indicative Prices (excl. VAT) from Linyang quotation LY202601271. Payment terms, civil works scope, and the binding Contract Price are fixed in each executed EPC using the Indicative and Confirmed Price mechanism (EPC §6.1).

4.2  Schedule 1 indicatives are valid for ninety (90) days from this LOI for planning. The Confirmed Contract Price for each park or batch is set when Lighthief issues the Confirmed Price Certificate under Clause 4.3.

4.3  (Two-way price commitment) Each EPC will state an Indicative Price (as in Schedule 1 or updated in writing before signing). Within fourteen (14) days after the Client receives grid Connection Terms for that park or batch, Lighthief will issue a Confirmed Price Certificate fixing the Contract Price. The Confirmed Price equals the Indicative Price unless the battery raw-material index (Mysteel lithium carbonate) or EUR/CNY moves beyond the thresholds in EPC §6.1 from the January 2026 reference values (155,000 CNY/tonne (Mysteel China battery-grade spot, January 2026 monthly average); 8.18 CNY per EUR (January 2026 average)). Where a threshold is exceeded, the Confirmed Price adjusts to reflect verified movement on the equipment cost base: downward adjustments are passed through to the Client on milestones not yet invoiced; upward adjustments are capped at five percent (5%) of the Indicative Price. If the calculated upward adjustment would exceed five percent (5%), either Party may decline to proceed with that EPC without penalty. Lighthief will provide a Price Basis Certificate at EPC signing (and at equipment delivery where applicable) showing the reference indices and calculation so the Client can verify how the price follows the market.

4.4  (Price lock — signature by 29 May 2026) The Parties acknowledge that, as of the date of this LOI, the Mysteel lithium carbonate index has moved materially above the January 2026 reference in Clause 4.3, while EUR/CNY remains within the EPC FX threshold. Schedule 1 therefore reflects pricing locked with Linyang on the January 2026 quotation basis, not today's spot index. Linyang has confirmed that where this LOI and the relevant park or batch EPC are executed on or before 29 May 2026, the Indicative Price (as in Schedule 1 or updated in writing before signing) shall be the Confirmed Price for equipment cost purposes, without upward raw-material or FX adjustment for index movement occurring before that EPC Effective Date. Clause 4.3 two-way adjustments apply after signing only to verified movement from the indices stated in the Price Basis Certificate at EPC signing.

5.   NEXT STEPS

5.1  The Parties will negotiate and sign the EPC package (EPC, LTSA, EMS addendum, and OEM warranties). Commercial terms for those documents are agreed in the EPC — not in this LOI.

6.   GOOD FAITH

6.1  The Parties will negotiate and sign the EPC package in good faith. If not executed within ninety (90) days of this LOI (unless extended in writing), either Party may withdraw without liability except Clause 1.3.

7.   EXCLUSIVITY

7.1  (Binding) Until this LOI expires or the relevant Schedule 1 EPC is signed, the Client will not appoint another EPC contractor for those parks or procure parallel BESS equipment for them from an OEM other than Linyang (Cyprus portfolio).

7.2  Exclusivity does not apply on Valid Reason (Clause 1.3) or if Lighthief has not proposed an EPC for signature within ninety (90) days of this LOI (unless extended in writing).

7.3  Exclusivity ends when the Schedule 1 EPC is signed, on Valid Reason, or if either Party materially breaches this LOI and does not remedy within thirty (30) days of notice.

8.   CONFIDENTIALITY

8.1  (Binding) Each Party shall keep confidential this LOI and related commercial, technical, and pricing information, except to advisers, lenders, or as required by law. This survives for five (5) years after this LOI ends.

9.   TERM AND GOVERNING LAW

9.1  This LOI runs until the earlier of: EPC and companion documents signed, eighteen (18) months from signing, or written termination.

9.2  Governed by Cyprus law. Courts of Cyprus have exclusive jurisdiction.

NATURE OF THIS DOCUMENT: Non-binding except Clauses 1.3, 7, and 8. Covers Galascope 1 & 2 only. Binding commercial terms are in the executed EPC and companion agreements.

SIGNATURES

IN WITNESS WHEREOF, the authorised representatives of the Parties have executed this Letter of Intent as of the date first written above.

| For and on behalf of Lighthief Cyprus Ltd | For and on behalf of Galascope Ltd |
| --- | --- |
| Name: Alexander Papacosta | Name: ___________________________ |
| Title: Managing Director | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

Lighthief Cyprus Ltd  |  HE 477423  |  28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus
office@lighthief.com  |  +357 77 77 00 50  |  solarfarms.cy  |  Ref: LCY-LOI-GAL-B1-2026-R15