| Lighthief Cyprus Ltd | LETTER OF INTENT LCY-LOI-ESP-PIPELINE-2026 April 2026 CONFIDENTIAL |
| --- | --- |

Letter of Intent — Esperia Energy Remaining Pipeline

Post-Galascope EPC Signing — 9 Parks | 72.25 MW | 287.5 MWh

1.  Background

This Letter of Intent (“LOI”) is issued by Esperia Energy Group (“the Client”), represented by Dino Constantinou (Owner), in favour of Lighthief Cyprus Ltd. Concurrently with the execution of this LOI, the Client has signed a binding EPC Agreement for the Galascope portfolio (Galascope 1: 5.0 MW / 20 MWh and Galascope 2: 2.5 MW / 8 MWh, Famagusta). This LOI confirms the Client's commitment to the full Esperia Energy pipeline as set out below, comprising nine (9) further parks across Famagusta, Limassol, and Nicosia districts.

| 9 Parks in Pipeline | 72.25 MW Total BESS Power | 287.5 MWh Total BESS Energy | €30,043,928 Indicative Value |
| --- | --- | --- | --- |

2.  Committed Pipeline — All Parks

The Client confirms its intention to execute EPC Agreements for the following parks, phased as indicated below. All pricing is indicative and based on Quotation LY202511281 / prevailing Lighthief group-order pricing schedule (ex. VAT).

| Park / Project | District | MW | MWh | Cont. | Indicative Price (ex. VAT) |
| --- | --- | --- | --- | --- | --- |
| Esperia Energy (Famagusta) | Famagusta | 6.50 | 20.0 | 4 | €2,316,815 |
| Esperia Green Energy (Limassol) | Limassol | 8.00 | 60.0 | 12 | €5,644,044 |
| Esperia Energy (Frenaros) | Famagusta | 25.00 | 100.0 | 20 | €10,088,014 |
| Phase 1 — 2026 Delivery — Subtotal |  | 39.50 | 180.0 | 36 | €18,048,873 |
| Esperia Green Energy (Famagusta 2) | Famagusta | 5.00 | 20.0 | 4 | €2,189,416 |
| Phase 2 — 2027 Delivery — Subtotal |  | 5.00 | 20.0 | 4 | €2,189,416 |
| Esperia Energy (Tseri) | Nicosia | 7.00 | 20.0 | 4 | €2,382,035 |
| Esperia Energy (Tseri 2-A) | Nicosia | 2.50 | 7.5 | 2 | €1,084,620 |
| Esperia Energy (Tseri 2-B) | Nicosia | 7.50 | 25.0 | 5 | €2,912,993 |
| Esperia Energy (Tseri 2-C) | Nicosia | 6.00 | 20.0 | 4 | €1,551,848 |
| Esperia Energy (Tseri 3) | Nicosia | 4.75 | 15.0 | 3 | €1,874,143 |
| Phase 3 — 2028 Delivery (Tseri Portfolio) — Subtotal |  | 27.75 | 87.5 | 18 | €9,805,639 |
| TOTAL PIPELINE (9 parks) |  | 72.25 | 287.5 | 58 | €30,043,928 |

3.  Phased Delivery & Conditions

Phase 1 — 2026 Delivery (3 Parks, 180 MWh)

The Client intends to execute EPC Agreements for the three Phase 1 parks (Esperia Energy Famagusta, Esperia Green Energy Limassol, Esperia Energy Frenaros) no later than Q2 2026. Target commissioning for all Phase 1 parks is Q4 2026, subject to EAC/DSO grid connection approvals.

Phase 2 — 2027 Delivery (1 Park, 20 MWh)

Esperia Green Energy (Famagusta 2, 5.0 MW / 20 MWh) is targeted for EPC execution in Q3 2027, with COD in Q1 2028. Execution is subject to grid connection approval from EAC for the Famagusta 2 site.

Phase 3 — 2028 Delivery (5 Parks, Tseri Portfolio, 87.5 MWh)

The Tseri portfolio (Nicosia district) comprising five parks is targeted for EPC execution in 2027, with staggered commissioning through 2028. Final specifications and split of Tseri 2 sub-entities are subject to confirmation.

For all phases, EPC execution is subject to:

Successful commissioning and performance verification of the preceding phase;

Availability of grid connection approvals from EAC / DSO;

Finalisation of site-specific technical designs (SCADA, SLD, MV/LV configuration);

Agreement on final pricing based on the prevailing Lighthief group-order schedule.

4.  Commercial Framework

Each EPC Agreement shall be executed on the following standard terms (indicative, subject to final contract negotiation):

30% advance payment upon contract signature / on or after 1 April 2026 (or applicable batch start date);

55% pre-shipment milestone (confirmed FAT / ex-works despatch);

10% at PAC (Provisional Acceptance Certificate);

5% retention released after 24-month Defect Liability Period (DLP).

Pricing shown is indicative based on Quotation LY202511281 (group-order rate). Final batch pricing will be agreed in writing no later than 60 days prior to the target EPC signature date for each phase.

5.  LTSA Framework

The Client confirms its intention to enter into a Long-Term Service Agreement (LTSA) covering all Esperia Energy and Galascope parks. The LTSA framework shall:

Commence for each park from its respective PAC date;

Apply a group-level 97% availability guarantee calculated across all Esperia/Galascope active parks;

Accumulate parks into the availability calculation progressively as each is commissioned;

Be priced on a per-MWh per-year basis in accordance with the agreed LTSA pricing schedule (Tier C or as separately agreed).

6.  Purpose of this LOI

This LOI is provided to Lighthief Cyprus Ltd to:

Confirm the Client's commitment to the full Esperia Energy BESS portfolio beyond the Galascope EPC;

Support Lighthief's procurement planning with its OEM equipment supplier (Linyang) for pipeline batches;

Evidence the pipeline for project financing, insurance, and DSO pre-application purposes;

Establish the basis for the group-level LTSA framework across the full Esperia / Galascope portfolio.

Non-Binding Statement: This LOI is a statement of intent and does not constitute a binding obligation to execute EPC Agreements for future phases. The binding commitment for the Galascope portfolio is contained solely in the EPC Agreement executed concurrently. Future phase EPC Agreements will be executed separately upon mutual written agreement of both parties.

7.  Signatures

| For Lighthief Cyprus Ltd | For the Client |
| --- | --- |
| Name: Alexander Papacosta Title: Managing Director | Name: ___________________________ Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

Lighthief Cyprus Ltd  |  HE 477423  |  28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus
office@lighthief.com  |  +357 77 77 00 50  |  solarfarms.cy