Solar PV — EPC Fixed-Price Offer

Option A — Fixed-Tilt · 825 kWp · Konia, Ierokipia, Paphos

Prepared for: TOTALCON LTD (HE 458896)   |   Attention: Mr. Qiu

July 2026   |   Ref: LCY-EPC-TOTALCON-KONIA-2026-07-A

EUR 550,000  fixed lump sum, PV turnkey (ex VAT) · EUR 0.67/Wp

825 kWp · 1,100 x RECOM Lion 750 W · fixed-tilt · LV, no transformer substation

Included in this fixed price

PV modules — 1,100 x RECOM Lion 750 W (Tier-1)

Fixed-tilt galvanised steel mounting structures

ETEK-certified engineering, SLDs, permit support, as-builts

Huawei string inverters + DC/AC BOS + monitoring

Site civils — grading, cut/fill, internal roads, drainage

Foundations & piling

Perimeter fencing, gates & security system (CCTV + perimeter intrusion)

Mechanical & electrical install, cabling, switchgear

Commissioning, SCADA, EAC witness-test & energisation

Logistics, cranage, HSE & project management

Key terms

| Item | Detail |
| --- | --- |
| Capacity | 825 kWp (fixed-tilt) |
| Grid | LV — no on-site transformer substation |
| Programme | ~7–9 months from advance payment |
| Payment | 30% signature · 40% delivery · 20% mechanical completion · 10% PAC |
| Retention / holdback | None — 12-month defects liability + warranty |
| Warranty | Modules 12/25-yr · inverters 5-yr · structures 10-yr · workmanship 2-yr from PAC |
| Validity | 60 days |

Indicative timeline (from advance payment)

| Phase | Duration |
| --- | --- |
| Engineering, permits & civils | 6–10 weeks (parallel with procurement) |
| Module procurement & shipping (China) | ~18–20 weeks — critical path |
| Install, cabling & switchgear | 6–8 weeks (after modules land) |
| Commissioning & EAC energisation | 3–4 weeks |
| Total (indicative) | ~7–9 months |

Optional add-ons (ex VAT)

| Add-on | Price | Detail |
| --- | --- | --- |
| BESS EPC — install only | EUR 70,000 | 4 MWh container (1 MW / 4 MWh, per CERA). Client supplies all battery equipment; Lighthief installs foundations, cabling, protection & commissioning support. |
| PV O&M — annual service | EUR 6,600 / yr | Preventive maintenance, panel cleaning, vegetation, SCADA monitoring, 6 corrective call-outs/yr. Fixed-tilt structure — no drive/actuator maintenance required. Separate LTSA from PAC. |

Not included (client responsibility)

EAC LV connection & transformer (charged by EAC on the connection offer); EAC testing/admin fees; building permit fees; off-site grid reinforcement; BESS hardware; VAT (19%).

Reference

CERA exemption E5229/2026 — 1 MWp PV + 1 MW / 4 MWh storage. Site: Temachio 150, Konia, Ierokipia, Paphos. Layout: OGT Energy Group, September 2025. Work commences on receipt of the 30% advance payment; permits and grid connection are the Client's responsibility and do not delay the works.

Lighthief Cyprus Ltd — EPC

Alexander Papacosta — Cyprus Director   |   Tel: +357 99 164 158   |   office@lighthief.com

28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol

Lighthief Cyprus Ltd  —  HE 477423  —  solarfarms.cy

28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus

Confidential — prepared for TOTALCON LTD. Fixed price ex VAT, valid 60 days.