INTERNAL — Meeting prep
Amit: Management implementation  |  Yossi: Sales & pipeline

June 2026 · Lighthief Cyprus Ltd · HE 477423

Classification: INTERNAL — not for client circulation. Figures from lib/portfolio-data.ts (May 2026). Verify against executed contracts before reliance. Do not share CIF, margins, or quotation references externally.

Meeting structure

| Segment | With | Focus | Duration |
| --- | --- | --- | --- |
| Part A | Amit | Implementation & management process | ~30–40 min |
| Part B | Yossi | Sales, pipeline, closes | ~30–40 min |

Shared anchor: Galascope Batch 1 (2 parks, 7.5 MW / 30 MWh, €3.44M ex VAT) — first execution test and first signed revenue gate.

Part A — Amit: Management & implementation

Opening line:

We are moving from deal packaging to repeatable EPC delivery: one confirmed batch (Galascope), then scale the same playbook across the group order and pipeline LOIs.

A1. Management model — who does what

Alexander Papacosta — Cyprus Director / programme owner: client, lender, Linyang/Voltus, commissioning presence.

Costas Hadjikyriacou — ETEK: DSO applications, witness test, planning, O&M team lead (Cyprus).

Andreas Christoforou — BESS consultant (UK → Cyprus): energy systems, specs, stakeholder support.

Field O&M — Dawid, Szymon, Kacper (Poland-trained, deploying to Cyprus).

Linyang — Kamil (install/SCADA), Michael (product), China commissioning team.

Subcontractors — civil, electrical install (TBD award), Soulis transport, Joha cables, DEHN LPS.

Lighthief = EPC integrator + O&M manager; client SPVs own assets. Single point of responsibility to client.

A2. Implementation phases (repeatable per batch)

| Phase | Duration | Owner | Management focus |
| --- | --- | --- | --- |
| 0 — Contract & CPs | Until EPC stamped | Alexander + legal | APG, DWU, CAR insurance, Disperon SHA rates |
| 1 — Pre-order | 6–8 weeks | Costas | DSO / connection terms, permits, civil design |
| 2 — Production | ~90 days | Linyang + Alexander | FAT, 55% pre-shipment milestone |
| 3 — Logistics | ~50 days | Alexander + Soulis | Permits 15 d; €2,500/container; Famagusta routes |
| 4 — Site EPC | Overlap G1+G2 | Costas + subs | Parallel installs — not sequential |
| 5 — Commissioning | → PAC | Costas + field | SCADA IEC-104, DSO witness |
| 6 — O&M handover | From PAC | Costas + engineers | LTSA, Voltus NOC, quarterly visits |

Galascope PAC target: 31 January 2027 (both parks). Production May–Jul 2026; ship Aug 2026; CIF Sep 2026.

A3. Galascope execution risks

| Risk | Management response |
| --- | --- |
| G1 and G2 in parallel (Famagusta) | Budget +0.3–0.7 FTE or site coordinator (~€15–45k overlap) |
| One supervisor, two crane windows | Second site cover or extended hours |
| PM load (Soulis, Linyang, DSO ×2) | Logistics / site admin fraction |
| Thin batch margin (~7.3% on €3.19M installed) | ~1% cost slip ≈ €32k; large overrun can wipe batch |

Decision for Amit: approve parallel programme with incremental supervision budget, or accept schedule/quality risk.

A4. Subcontractor & procurement governance

| Workstream | Status | Action |
| --- | --- | --- |
| Civil (€2,000/MWh) | Confirmed | Monitor subcontractor delivery |
| Transport (A. Soulis) | Confirmed | Per-container playbook |
| Cables (Joha) | Per-park quoted | Cost control per park total |
| Electrical install | No RFP awarded | PRIORITY — blocks execution |
| CAR insurance | Marsh in progress | Bind before Linyang advance |
| EMS/SCADA (Voltus) | Quoted | SHA Exhibit C rates — 14 days post-sign |

A5. O&M management ramp

Portfolio (active model): 29 parks, ~517 MWh — Galascope adds 30 MWh.

Monitoring: Voltus SCADA + Lighthief NOC 24/7.

Recommended field staffing: 5 engineers (2 night / 2 day / 1 float); ~320 night shifts/year (batched).

Planned maintenance: midnight–6am; critical response 1 hr remote / 4 hr on-site.

Engineers completing 3-week Czestochowa training (BMS, PCS, EN 50549-2, DSO witness).

LTSA ~€1,740/MWh/yr — separate revenue stream; do not under-resource because EPC margin is tight.

A6. Governance & resourcing

Origination pool (up to 30% net margin): existing Cyprus team that built backlog — not new hires unless agreed.

Galascope EPC sign triggers operational scale (MD salary step, parallel investor tracks).

Investor-introduced staff: separate employment/advisory terms; no automatic commission on closed deals.

A7. Questions for Amit

What management systems expected (PM tool, weekly cadence, milestone dashboard)?

Staffing Cyprus PMO vs advisory only?

Cap on parallel sites before dedicated programme manager?

PV-O&M integration — shared field team or separate BESS unit?

A8. Amit — next 30 days

| # | Action | Owner |
| --- | --- | --- |
| 1 | Galascope EPC signed | Alexander + Dino |
| 2 | Electrical subcontractor awarded | Alexander |
| 3 | CAR insurance bound | Alexander |
| 4 | Parallel site programme issued | Costas / PM |
| 5 | O&M roster confirmed for PAC window | Costas |

Part B — Yossi: Sales & pipeline

Opening line:

Cyprus BESS sales are relationship-led group orders — Esperia/Galascope is the anchor; the rest of the ~€61M group backlog follows the same EPC + LTSA product.

B1. Product (client language)

| Layer | What the client buys |
| --- | --- |
| Turnkey EPC | Linyang BESS + install + commissioning + grid witness support |
| LTSA | 15-year O&M, availability, performance management |
| EMS/SCADA | Voltus/Disperon — €400/MWh/yr (Galascope model) |
| Extended warranty | Yrs 6–15 — paid direct to Linyang (not Lighthief P&L) |

Elevator pitch: Exclusive Linyang distributor; largest Cyprus utility-scale BESS rollout; single contractor from container to PAC; ETEK sign-off and DSO coordination included.

B2. Pipeline funnel

Active model: 29 parks · ~517 MWh · ~€64M revenue when fully contracted (28 group + Aeolian).

| Priority | Client | MWh | Probability | Revenue (approx) | Sales action |
| --- | --- | --- | --- | --- | --- |
| 1 | Galascope (Esperia) | 30 | Confirmed — legal | €3.44M | Support counsel; hold G1/G2 price |
| 2 | Spanercom (Anarita ×2) | 40 | ~85% | ~€4.76M | EPC day after Galascope sign |
| 3 | Timotheos (9 parks) | 81 | ~50% | ~€11.8M | EPC signature for B1 slot |
| 3 | Lampros (2 parks) | 15 | ~50% | ~€2.1M | Same |
| 4 | Esperia pipeline LOI | 285+ | Post-Galascope | ~€33M+ | Batches 2026–28 |
| 5 | Aeolian (wind hybrid) | 20 | ~85% | €2.66M | Separate track |
| Park | Kerasi / Karis | 45 | ~30% | ~€6.3M | After B1 committed |
| Lost | ABIO | 200 | ~20% | — | Lost to CATL; do not forecast |

B3. Galascope — closed vs still selling

Closed commercially (May 2026):

G1: €2,238,000 (20 MWh effective); G2: €1,206,300 (10 MWh).

Payments: 30 / 55 / 10 / 5; 3-month DLP; PAC 31 January 2027.

Still with counsel (do not re-trade price):

APG transfer to Galascope / Alpha Bank.

EMS addendum €400/MWh/yr for 5 years from PAC.

Scope: Costas sign-off included; licensed site drawings excluded (€5–15k/site).

Do NOT say in client meetings: CIF, margins, quotation numbers, internal pipeline totals.

B4. Sales narrative by segment

Esperia / Dino: Galascope proves model for 9-park pipeline LOI; split LOIs reduce legal drag.

Spanercom: Same hardware as Galascope G1; ~€119k/MWh — send EPC immediately after Galascope stamp.

Timotheos / Lampros: Verbal intent — urgency: sign by Jun 2026 or lose B1 production slot.

Aeolian: Wind + BESS flagship; €2.66M turnkey — marketing and standalone close.

B5. Competitive positioning

| Objection | Response |
| --- | --- |
| CATL / €124k/MWh flat (ABIO) | We sell turnkey EPC + grid compliance + LTSA, not container-only |
| Cheaper container quote | Client still needs civil, DSO, SCADA, install — our price is installed PAC |
| 6-month DLP ask | 3 months with stronger bank security package |

B6. Revenue phasing (forecast)

| Wave | Timing | MWh (approx) | Note |
| --- | --- | --- | --- |
| B1 Galascope | Sign → PAC Jan 2027 | 30 | Advance after Connection Terms |
| B1 extension | If 7 parks sign | 90 | Same slot as Galascope |
| Esperia 2026 pipeline | Post-trust | 75 | LOI batch 2 |
| 2027 / 2028 | LOI | 115 + 125 | Frenaros 100 MWh flagship 2028 |

B7. Origination & incentives

Up to 30% of net margin on executed projects → existing Cyprus origination team (pre-investment).

New sales hires / investor-introduced personnel → outside pool unless expressly agreed.

Clarify Yossi role: closing vs origination vs channel (Israel / EU) before promising commission.

B8. Prospecting (beyond funnel)

| Director / group | BESS MW | Angle |
| --- | --- | --- |
| Timotheos Timotheou | 61 | Already in funnel — deepen |
| HELIOPEX (Patssalis / Kallenos) | 13 each | Post-B1 hybrid EPC |
| GKA Georgiou | 6.4 | Smaller hybrid |
| Santiam / Stephanidis | 0 BESS | PV O&M cross-sell only |

B9. Questions for Yossi

Which accounts does he personally own vs support?

Israel / EU channel — exclusive or introducer?

After Galascope: Spanercom first or Timotheos block for volume?

Need one-page commercial summary for new meetings?

B10. Yossi — sales targets

| # | Target | By |
| --- | --- | --- |
| 1 | Galascope EPC + EMS addendum signed | ASAP |
| 2 | Spanercom EPC issued | 48h after Galascope |
| 3 | Timotheos + Lampros chase meetings | Jun 2026 |
| 4 | Aeolian signature path | Q2 2026 |
| 5 | Esperia 2026 pipeline LOI paper | Post-Galascope / Q3 2026 |

Handoff (30 seconds)

To Yossi (after Amit): Management is building the delivery machine for Galascope; sales must stamp Galascope then clone the contract to Spanercom and B1 extension (~€10M+ ex VAT in 90 days if executed).

To Amit (before Yossi): Sales holds €3.44M at counsel; execution prep cannot wait for ink — electrical sub and parallel site plan must run in parallel.

Lighthief Cyprus Ltd · HE 477423 · office@lighthief.com · +357 99 164 158 · solarfarms.cy
Prepared June 2026 · Source: lib/portfolio-data.ts · INTERNAL