INTERNAL — Esperia / Galascope — Pre–client meeting notes
Wednesday 20 May 2026

Lighthief Cyprus Ltd · HE 477423 · Classification: INTERNAL — not for circulation to client without review. Summarises internal discussions (commercial, bank, guarantees, insurance, contract stack). Not legal or financial advice.

1. Contract & programme status (Galascope / Esperia)

Galascope Ltd — two BESS sites (Galascope 1: 5 MW / 20 MWh; Galascope 2: 2.5 MW / 10 MWh), Famagusta, hybrid Category B.

Full EPC package (draft for signature) with Esperia side: EPC (LCY-EPC-001 v5.0 baseline; v5.1 commercial/schedule mechanics where applicable), LTSA, EMS addendum, OEM Direct Warranty Undertaking (Linyang). Status discussed: with client (Dino / Esperia) for legal review — confirm actual status on the call.

Upstream: Linyang sales contract (17 Mar 2026 baseline) recorded as executed in internal SSOT; operational gates still include APG before relevant advances to Linyang and construction-phase insurance per risk checklist — confirm with counsel what is already satisfied.

Internal bankability brief (May 2026) is NOT client-facing; client-facing materials are the executed/issued contract pack and curated summaries without internal repo paths or sensitive terms.

2. Payment waterfall (headline model)

Client → Lighthief (internal model): 30% advance; 55% pre-shipment; 10% PAC; 5% retention (SSOT text — align to signed EPC §7.1).

Lighthief → Linyang (internal model): 20% advance; 50% pre-shipment; 20% DAP; 10% SAT — align to executed sales contract.

Cash timing: after client 85% and Linyang 70%, the next Linyang 20% (DAP) can create a short window vs client PAC 10% — model per project; consider WC or milestone alignment.

Reconcile SSOT “24-month DLP” retention wording with EPC v5 bankability narrative (3-month DLP) before any client-facing schedule cites retention release.

3. Advance Payment Guarantee (APG) — how it works

APG is issued by Linyang’s bank (applicant Linyang) for the benefit of Lighthief as buyer — secures refund/reperformance if equipment prepayments are taken and supply fails.

Operational rule: do not remit Linyang equipment prepayments until an acceptable APG is in hand (condition precedent in the sales/EPC chain — exact clause per executed documents).

This does NOT replace possible separate security that the client’s bank (e.g. Alpha) may want from Lighthief for the client’s advance (different direction: contractor / bank to employer or security agent).

4. Bank of Cyprus & Alpha / lender context

BoC relationship is young (from 1 July); modest cumulative flows (~€200k discussed internally). Expect limited appetite for large unsecured on-demand bonds — early discussion with Trade Finance / Guarantees and RM (Marianna) to size realistic products.

Alpha (or other lender) will drive CPs for the borrower; Lighthief must map what BoC can actually issue vs what Alpha asks (advance payment bond, performance bond, escrow, LC).

If corporate bonds are not available unsecured, fall back to: escrow / controlled account, client-side LC, lower advance %, smaller tranches, cash-covered surety, or (if acceptable) JV with established EPC balance sheet.

5. Newco / no completed BESS EPC under Lighthief Cyprus

Treat lack of Cyprus EPC completion history as normal: credit story for thin SPV is usually structural (escrow, LC, OEM APG, insurance, delivery chain bios) plus any group experience presented accurately — not as blanket cross-guarantee unless counsel structures it.

6. Sinosure / export credit (Linyang side)

Sinosure-style cover is typically for commercial credit risk; if milestones are truly client-funded and APG gates upstream prepay, clarify with Linyang counsel exactly which product and premium they require and whether it applies to fully prepaid tranches.

7. Poland bank guarantee samples

Useful as non-binding format / negotiation examples only; not legally portable. Each deal needs a new instrument matching applicant, beneficiary, contract reference, amount, currency, law, and EPC/Linyang definitions.

8. Escrow option (client cash + Linyang payment)

Client funds escrow; release to Lighthief when objective CPs are met (e.g. APG + documentation); Lighthief pays Linyang same day / back-to-back from cleared funds.

Direct escrow-to-Linyang splits are possible but need Linyang acceptance, bank KYC, and tax/invoice alignment.

9. Holland (NBI) insurance supplementary pack

Internal exposure schedule to Holland Verzekeringsmakelaars: strong numerics for CAR/DSU/LD, but treat as underwriting appendix; add explicit broker asks, deadlines, and market minimums if used as formal RFP.

Fix internal inconsistencies before re-issue (park/MWh totals vs subtitle; total EPC sum reconciliation; EPC version cite should match current v5 / v5.1 stack).

10. Scope & pricing clarifications for Dino (group / Galascope)

Show group-proposal.html scope page: included vs excluded split is now explicit.

INCLUDED in group €/kWh: Costas Hadjikyriacou ETEK installer sign-off (installation compliance, protection settings attestation, EAC liaison for BESS compound); Lighthief coordinates and attends DSO witness; full commissioning.

EXCLUDED: licensed electrical design / permit / as-built drawing packages for the wider site (€5k–15k/site typical — Client's engineer); EAC/DSO inspection and protection-test invoices; external LPS; telecom OPEX.

Key message: installer sign-off ≠ licensed design drawings — confirm Dino understands before signature; mirror in EPC Schedule A.

See meeting-dino-terms-may2026.md for verbatim talking lines.

11. Suggested talking points — commercial / legal

Confirm signing timeline and any Alpha CPs already known.

Confirm milestone dates vs batch CIF/PAC assumptions.

Agree communication path for bond/escrow/LC if lender is in the loop.

No internal quotation refs or margin language in client-visible follow-ups.

Prepared from internal working notes. Verify all figures against executed contracts and lib/portfolio-data.ts before reliance.