ENGINEERING, PROCUREMENT AND CONSTRUCTION (EPC) CONTRACT OF

A PHOTOVOLTAIC PARK OF 3,15 MWp IN SIA (CYPRUS)

This is an extract of the Contract, describing the business terms to be negotiated.

The Employer and the Contractor (the “Parties”) agree as follows:

- Interpretation

In this Contract words and expressions shall have the same meaning as are respectively assigned to them in the Specifications attached to the Contract as Appendix A (the “Specifications”).

- Documents Forming Part of the Contract

The following documents shall be deemed to form and be read and construed as part of this Contract (the “Contract Documents”):

  - Technical Specifications, Drawings, Bill of Materials

The Specifications containing the General Conditions of Contract and the Technical Specifications to be provided 30 days after the signature of this contract and as may be amended in the future by agreement between the Parties, comprise the following documents:

    - Technical Description (TD) of the Project setting out the scope of Works and comprising the following:

      - High-Level Description of Project Documentation

      - Power Plant General Description

      - Civil Works and Mounting System

      - Power Installations

      - Grounding Systems & Lightning Protection

      - Security Systems

      - Plant Monitoring and Surveillance System

      - Fire Protection

      - Engineering Standards and Code

    - Mounting System comprising the following:

      - Bill of Quantities

      - Warranty

      - Assembly

      - Static Calculations

      - Cross Section Description

      - Design Analysis

      - Technical Manual

      - Technical Description

    - Drawings comprising the following (Submission List):

| A.01 | GENERAL LAYOUT | 1/500 |  |
| --- | --- | --- | --- |
| A.02 | MOUNTING LAYOUT | 1/500 |  |
| A.03 | CABLE TRENCH LAYOUT | 1/500 |  |
| A.04. | AC LAYOUT | 1/500 |  |
| A.05 | DC LAYOUT | 1/500 |  |
| A.06 | SECURITY LAYOUT | 1/500 |  |
| A.07 | LIGHTING LAYOUT | 1/500 |  |
| A.08 | EARTHING LAYOUT | 1/500 |  |
| A.09 | LIGHTNING LAYOUT | 1/500 |  |
| A.10 | FIRE PROTECTION LAYOUT | 1/500 |  |
| A.11 | MONITORING LAYOUT | 1/500 |  |
| A.12 | ROAD-FENCE-GATES LAYOUT | 1/500 |  |
| A.13 | EAC SS | 1/50 |  |
| A.15 | DETAIL DRAWING |  |  |
| B.01 | PRODUCTION SINGLE LINE DIAGRAMM | D |  |
| B.02 | AUXILIARIES SINGLE LINE DIAGRAMM | D |  |
| B.03 | SECURITY DIAGRAM | D |  |
| B.04 | MONITORING & COM. DIAGRAM | D |  |
| C.01 | AC CABLE CALCULATIONS | DOC |  |
| C.02 | DC CABLE CALCULATIONS | DOC |  |
| C.03 | EARTHING CALCULATION | DOC |  |
| C.04 | LIGHTNING CALCULATION | DOC |  |
| C.05 | AUXILIARIES & UPS LOADS | DOC |  |
| C.06 | ENERGY STUDY | DOC |  |

    - Bill of Materials used for the Project

The bill of materials is attached herewith in Table 1 and is for reference purposes only. If additional materials will be required during construction, these will be provided by the Contractor without any extra charge to the Employer.

    - Calculations comprising the following:

      - AC Power Losses and Voltage Drop Calculations

      - DC Power Losses and Voltage Drop Calculations

      - Lightning Risk Assessment

      - Ground Resistance and IEEE St80 Calculations

      - Dimensioning of the Auxiliaries, UPS Loads and Energy Consumption

      - Energy Study (Performance Ratio and Specific Production/KWp/Year using PVSYST, PVSOL, Polysun or other similar SW) and

      - Simulation of minimum losses for PVSYST, PVSOL, Polysun or other similar SW Calculations

    - Specifications and warranties of Contractor-supplied Equipment comprising the following:

      - PV Panels

      - Inverters

      - Mounting Systems

      - Medium Voltage (MV) Switchboard

      - Low Voltage (LV) Switchboard

      - AC Cabling

      - DC Cabling

      - Communications Cabling

      - Earthing System

      - Lightning Protector

      - Lighting

      - SCADA System

      - Monitoring Systems

      - Security System

    - Spare Parts

    - Geotechnical Survey

    - Hydrological Study

    - Construction Quality Plan

  - Contractor Information

The following Annexes comprise the details related to the Contractor, its Suppliers and Subcontractors:

      - Annex A: List of Subcontractors to the Contractor and/or any associates

      - Annex B: Suppliers of main Contractor and supplied Equipment

      - Annex C: Description of Contractor’s firm, its experience and financial standing

      - Annex D: List of proposed work team/key personnel for the construction work at site

      - Annex E: Curriculum Vitae (CVs) of key personnel)

The Contractor shall comply with all relevant labour and social security laws applicable to Contractor's personnel and subcontractors, including laws relating to their employment, health, safety, welfare, immigration and emigration, and shall allow them all their legal rights. The Contractor shall require its employees to obey all applicable laws, including those concerning health and safety at work.

  - Implementation Schedule

The Implementation schedule for the Project is attached herewith in the form of a Gantt Diagram in Appendix B (the “Implementation Schedule”).

  - Representatives

Employer and Owner shall each designate a representative ("Designated Representative") to act on its behalf in overseeing the performance of this Agreement.  Employer and Owner may change their respective Designated Representatives upon written notice to the other party given as provided in this Agreement.  Designated Representatives shall be the primary means for communication and all other interactions between Employer and Owner that are required under this Agreement.  Designated Representatives shall have the power and authority to bind their respective principals under the terms of this Agreement, with any required internal corporate approvals with respect to such authority being the responsibility of each representative to obtain from his or her principal.

  - Operation and Maintenance

The Operation and Maintenance Agreement for the first two years of operation, which starts after the issue of the Taking-Over Certificate, is attached herewith as Appendix C.

.

- Contractor’s Obligations and Guarantees

The Contractor shall carry out his obligations under the terms of the Contract with reasonable skill and care, per the technical guide of EAC, incorporated in the final terms of connection of the Project to the grid as annex 1 (the “Technical Guide”, https://www.eac.com.cy/EL/RegulatedActivities/Distribution/renewableenergy/Documents/Traditional%20Regulation/%ce%a4%ce%95%ce%a7%ce%9d%ce%99%ce%9a%ce%9f%ce%a3%20%ce%9f%ce%94%ce%97%ce%93%ce%9f%ce%a3%20-%20%ce%a3AA%ce%97_%ce%95%ce%9a%ce%94%ce%9f%ce%a3%ce%97%202023.2.pdf) annex A (“Special, Technical and Other Terms”, https://www.eac.com.cy/EL/RegulatedActivities/Distribution/renewableenergy/Documents/Competitive%20Market/%ce%a0%ce%91%ce%a1%ce%91%ce%a1%ce%a4%ce%97%ce%9c%ce%91%20%ce%91_%ce%b5%ce%b9%ce%b4%ce%b9%ce%ba%ce%bf%ce%af%20%cf%84%ce%b5%cf%87%ce%bd%ce%b9%ce%ba%ce%bf%ce%af%20%cf%8c%cf%81%ce%bf%ce%b9_%ce%a3%cf%87%ce%ad%ce%b4%ce%b9%ce%bf%20%ce%94%ce%a3%ce%94_%ce%a3.%ce%91.%ce%91.%ce%97%20%2013-03-19.pdf) thereto, and “Lightning Protection and Surge Protection Technical Manual for Outdoor Photovoltaic Installations” (https://www.eac.com.cy/EL/RegulatedActivities/Distribution/Documents/Area.PDF) located at the website of EAC,   and to the best of his ability and shall ensure that his employees, associates and subcontractors shall carry out the Works necessary to meet the Contractor's contractual obligations so that the Works, as these are set out in the Technical Specifications, are fit for purpose, in other words, to generate electricity per its permits and licenses and the laws of Cyprus.

Before the commencement of any Works, the studies, plans or designs, including static studies, in connection with the Works (the “Designs”), and irrespective of the inclusion of such Designs in this Agreement as annexes, attachments or otherwise, shall: a. be submitted by the Contractor to TUV Cyprus, as project manager (which will be appointed by the Employer, and shall be herein referred to as the “Project Manager”) for its prior approval, b. comply with the applicable laws and regulations of the Republic of Cyprus (including for the avoidance of doubt, any appliable regulations of ETEK), c. be amended in accordance with any reasonable instructions of the Project Manager and its consultant (the Supervising Engineer - επιβλέπων μηχανικός («SE»)) for ensuring compliance with the applicable laws and regulations of the Republic of Cyprus (including for the avoidance of doubt, any appliable regulations of ETEK).

In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to design, execute and complete the Works and remedy any defects therein, in conformity with the terms and provisions of this Contract. More specifically the following terms shall apply:

  - Warranty Period, Defect Liability Warranty

The "Defect Liability Warranty Period" is calculated from the date of issue of the Taking-Over Certificate and shall extend for a period of two (2) years. The Contractor Warrants that it shall be responsible for making good by repair or replacement as soon as possible at his expense any defect in or damage to any part of the Works which may appear or occur during the Defect Liability Warranty Period and which may arise either:

- From any defective materials, workmanship or design in the Contractor-supplied Equipment and in connection with the Works, or

- From any act or omission of the Contractor which causes loss or damage to any part of the Project.

In case of delays in responding to and resolving possible defects as above, and as described in Clause 2 of the attached O&M Agreement, the Contractor shall be liable to pay liquidated damages in accordance with Clauses 3.5.2 and 3.5.3 below.

The Defect Liability Warranty Period will be terminated after the expiry of the two-year period, provided that the Supervising Engineer (“SE”) of the Employer confirms that the conditions for completion of the Defect Liability Warranty Period have been met. In order to make this confirmation, no less than ten days before the expiry date, the SE shall inspect the Project in order to verify that:

- the Project runs appropriately,

- the production is in accordance with the Guaranteed PR,

- the PV Panels are clear and clean.

Only if these conditions are satisfied shall the SE issue the Defect Liability Warranty Termination Certificate.

  - Guaranteed Response Time to Faults or Defects

The Contractor guarantees that it shall respond in relation to a fault or defect within 24 hours after identifying the fault or defect itself from the O&M monitoring system, or after a notification is sent by email or telephone call to the agreed representative of the Contractor by the Employer. The Contractor shall correct any fault or defect as soon as reasonably practicable. For the avoidance of doubt, any downtime due to a fault or defect will be taken into consideration when calculating the percentage of Availability in accordance with Clause 3.3.

  - Project Guaranteed Availability per Year

The Contractor guarantees that the percentage of the total hours of daylight during which the Project and all PV Modules are in full working order and able to generate electricity (the “Availability”) shall be at least 98,0% in each year of operation during the two-year O&M and PR guarantee period. In the event that the Availability falls below 98,0%, the Contractor shall be liable to pay liquidated damages as per Clause 3.5.3 below, corresponding to the difference in hours of energy production between the 98,0% projected energy-producing hours (based on information from functioning parts of the Project and/or neighbouring projects) and the actual energy-producing hours measured.

  - Guaranteed Time of Completion

The Contractor guarantees that it shall complete each specific item and all of the Works, in accordance with Implementation Schedule. The time set out in the Implementation Schedule as the time of completion of all the Works shall be referred to as the ‘Guaranteed Time of Completion’.

The Contractor provides the above guaranteed time for completion of the Works (excluding the Grid connection Works to be performed by the EAC as per Clause 2.1 of the Specifications), having duly noted his liability under the General Conditions of Contract for delay in completion, which provides that in case the Contractor fails to complete the Works within the guaranteed time limit, there shall be deducted from the Contract Price or paid to the Employer by the Contractor as liquidated damages the amount of 100€ (two hundred Euros) per MWp installed capacity (as per Clause 3.5.1 below) for each day of delay between the ‘Guaranteed Time of Completion’ and the actual date of Completion. In case of prolonged delays, attributable to the Contractor alone, exceeding 4 (four) weeks, the Employer has the right to cash the Performance Guarantee if applicable during the Construction Period as per Clause 3.6 below, carry out any Works with contractors of the Employer’s choice at a reasonable cost to be borne by the Contractor and/or terminate the Contract, without prejudice to any other action that the Employer may take for further damages due to the delays in addition to or irrespective of termination.

In case there is any delay in the payments as per Clause 4, the time of completion is postponed by an equal number of days as these delays.

  - Liquidated damages

The Liquidated Damages shall be €100 per MWp per day for:

    - delay in completion of the Works as per Clause 3.4 above;

    - delay in resolving matters related to defects, omissions, etc, not affecting production, at a mutually agreed time, as per the instructions of the Employer’s representative; and

    - the number of days or part days corresponding to the difference between the guaranteed Availability of 97,0% and the availability measured in case it is lower than 95,0% as per Clause 3.3 above.

  - Performance Guarantee During the Construction Period

Intentionally Left Blank.

  - Advance Payment

There shall be an advance payment on the part of the Employer equal to 75% of the contract value.

  - Operation and Maintenance (O&M)

The Contractor shall provide Operation and Maintenance services for the first two years after the issue of the Taking–Over Certificate. The services to be offered and their respective cost are described in detail in the attached Operation and Maintenance Agreement (Appendix C). The Defects Liability Warranty as per Clause 3.1, the Liquidated Damages as per Clause 3.5 and the Performance Guarantee as per Clause 3.6 above shall also be applicable for the O&M Agreement where mentioned either herein or in the O&M Agreement.

  - Transfer of Ownership and Risk

Each item of the Works to be performed and Equipment to be supplied by the Contractor under this Contract shall become the property of the Employer, free from liens and other encumbrances, on the earliest occur of the following:

(a)	when the item of the Works or Equipment is delivered to the Project site; or

(b)	when the Contractor receives payment for the item of the Works or Equipment.

The risk of loss and damage to the Equipment and the Works shall be transferred to the Employer on the date of issue of the Taking-Over Certificate.

- Price Breakdown and Schedule of Payments

The Employer hereby covenants to pay the Contractor, in consideration of the design, execution and completion of the Works and the remedying of any defects therein, the final Contract Price, as agreed and analysed below.

xxx

The above Contract Price is firm and shall be all-inclusive, considering any taxes, duties, charges, contract stamp fees, etc., that may be payable in Cyprus, but not including VAT.

The Contractor will be paid by the Employer according to the progress of the Works, as described in detail in the Payment Schedule below. Payment shall be made after the Contractor sends in writing the required documentation for payment to the Employer. The Project Manager within 3 working days will certify or reject the performed work and within another 2 working days, the Employer will approve payment if the Project Manager so certifies in accordance with any requirements, the results of any applicable tests and the commissioning of the Project according to the Technical Guide and the European Standard EN62446-1:2016/A1:2018: Grid-connected photovoltaic systems–Minimum requirements for system documentation, commissioning tests and inspection (IEC62446-1:2016/A1:2018). The corresponding payment will be made seven (7) days after the approval of the Employer. The Contractor is obliged to pay promptly his sub-contractor for work performed by the specific sub-contractor. In case the Contractor delays to pay promptly the sub-contractor, the Employer can at its discretion directly pay the corresponding amount to the sub-contractor and subtract it from the next payment of the Contractor, provided that the Employer has notified in writing the Contractor of its (the Employer’s) intention to make such payment seven (7) days before such payment. In this respect, prior to any disbursement/payment to the Contractor, the Contractor shall provide proof of his previous payment to the sub-contractors through SWIFT, as per the individual schedule of payments agreed between the Contractor and the sub-contractor.

- Effective Date of Execution of the Contract

The Contract shall come into full force and effect after the financing of the project has been secured by the Bank and or on a date mutually agreed by the Parties. In any case, this date shall be one week after the payment of the first down payment as per clause 4., milestone (2) and the preparation of the Health & Safety Plan and Waste Management Plan by the Contractor (Appendix D).

- Indemnity

The Contractor shall accept full responsibility for any neglect, error or omission of itself or of its employees, agents suppliers and sub-contractors in carrying out the duties and obligations under or in connection with the Contract, and shall indemnify and keep indemnified the Employer from any proceedings, actions, claims, demands, losses, costs and expenses which may be brought or made against or sustained or incurred by the Employer because of or however arising out of any breach of the terms of or failure in this Contract, any breach of applicable law, any infringement of a third party’s rights and/or any other act or omission of the Contractor or its employees, agents suppliers and sub-contractors in the performance or non-performance of its obligations under this Contract.

The Contractor warrants and undertakes to the Employer that in the performance of the Works, it shall exercise the skills, care and diligence to be expected of a properly qualified and competent Contractor, experienced in carrying out Works in respect of projects of similar scope and complexity to the Project.

The Contractor shall at all times carry a Professional Indemnity Insurance in order to cover his obligations and duties under the Contract.

- Termination

Notwithstanding any other provisions in the Contract, the Employer may terminate this Contract and seek damages or remedies on the grounds foreseen by the Laws of Cyprus and/or in the circumstances foreseen in this Contract and/or for any of the following causes:

- The Contractor not performing according to his obligations including unjustifiable delays, noncompliance with the Specifications and generally for material breaches of any of the provisions of the Contract and the Contract Documents and fails to cure such breach within 15 days. Material breaches include breaches of contractual obligations by the Contractor that according to this Contract shall give the right to the Employer or the Authorities to seek remedial actions or Damages, including any Employer’s cost for carrying out any Works not performed by the Contractor in accordance with this Agreement.

- Material breaches of the Health and Safety Plan and respective legislation and failure to cure such breach within a period of 15 working days or the deadline set by the appropriate health and safety inspectors, whichever is the sooner.

- If the Contractor ceases to provide Works without justifiable cause for a period in excess of five (5) consecutive working days or eight cumulative working days in a month.

- Subcontracting any part of the Works without the consent of the Employer as foreseen in the Contract Documents.

The Contractor may terminate the Contract in case of material breaches by the Employer regarding his contractual obligations, including substantial delays in payments of works already performed by the Contractor and certified for payment by the Project Manager (more than 30 days). Also, for the two-year O&M period, the Contractor may terminate the Contract if the Employer ceases to provide to the Contractor physical access to the Project site. Notwithstanding the aforementioned, the Contractor shall not be entitled to terminate the Contract unless it first gives written notice to the Employer identifying the relevant breach and requiring the Employer to cure the breach and the Employer fails to cure the breach within 30 days from receiving the notice or, if the breach is not curable within 30 days, within such period of time as is reasonably necessary, but in no event more than 90 days, provided that the Employer diligently commences and continues to pursue such cure.

Each Party’s right to terminate the Contract shall be exercised by sending to the other Party a prior notice describing in detail the reasons for the proposed termination. After the receipt of the notification for the termination of the Contract, by either Party, the Parties will proceed to determine the quantity of Works delivered and correctly carried out and then issue the Certificate of Verification of Finished Works. At this time, a calculation will be made of the amount receivable by each Party, including duly certified losses and/or damages suffered by the Parties as a consequence of the early termination. The amounts shall be paid according to the provisions of the Contract.

- Confidentiality

  - Mutual Obligations

    - Each Party agrees to keep the confidential information of the other Party confidential, using the same degree of care that it exercises with respect to its own proprietary information, but in no event less than reasonable care, and may use it only for the purposes for which it was provided under the Contract. Information that is considered confidential includes information about the corporate entities and the business of each Party, trading information, financial information and project designs and procedures (in general data that is related to the implementation of the Projects).

    - The Party in receipt of confidential information shall be responsible for the safekeeping thereof and the copies that it may have of the same provided by the other Party for the purposes of keeping the confidential information confidential, private and restricted, and it must return them to the disclosing Party or destroy them upon the termination of the Contract, or before, if so required by the disclosing Party.

    - Notwithstanding anything to the contrary, each Party and its personnel shall be entitled to use any residual knowledge that it may acquire, gain and/or receive during the term of the Contract.

  - Exceptions

The obligations of Section 8.1 do not apply to information which:

- is rightfully obtained by the receiving Party from a third party who was not under any non-disclosure obligations;

- is, or becomes known to the public at the time of disclosure, or became generally known to the public after disclosure without breach of the Contract;

- was known to the receiving Party without such restrictions prior to its receipt from the disclosing Party;

- was disclosed with the prior written approval of the disclosing Party;

- was disclosed in response to a valid court or governmental order;

- was disclosed only to personnel who have agreed in writing to similar confidentiality restrictions and to the degree that is necessary for the fulfilment of the obligations of the receiving Party under this Contract; or

- was disclosed to the Bank or other financial institution which has provided finance for the construction and operation of the Project.

- General Provisions

  - Stamp Duty

The Contractor shall be liable for any stamp duties imposed by the relevant laws of the Republic of Cyprus.

  - Notices

All notices, that either Party desires to send to the other Party shall be sent, either via personal delivery, by any courier which regularly provides receipts, by registered or certified first class mail, return receipt requested and postage prepaid, or e-mail, to such Party at its address as set forth herein or such other address as such Party may designate by notice in writing to the other Party.

Any such notice shall be deemed to be delivered, given and received for all purposes as of: (i) the date so delivered, if delivered personally; (ii on the date of receipt or refusal indicated on return receipt, if sent by registered or certified first class mail, return receipt requested, postage and charges prepaid and properly addressed, or (iii) upon confirmed receipt, if sent by e-mail.

  - Entire Agreement

This Contract contains the entire agreement of the Parties and there are no other promises or conditions in any other Contract whether oral or written. This Contract supersedes any prior written or oral agreements between the Parties.

  - Severability

If any provisions of this Contract shall be held to be invalid or unenforceable for any reason, the remaining provisions shall continue to be valid and enforceable. If a court finds that any provision of this Contract is invalid or unenforceable, but that by limiting such provision it would become valid or enforceable, then such provision shall be deemed to be written, construed, and enforced as so limited.

  - Limitation of Liability

Without prejudice to the specific liquidated damages payable by any Party, as provided expressly in this Contract, the total liability of the Contractor is limited to x% of the Contract Price.  This limitation shall not apply in the event of wilful default or gross negligence on the part of the Contractor.

  - Assignment

Neither Party may assign its rights or delegate its obligations under this Contract to a third party in whole or in part, except with the other Party’s prior written consent, which shall not be unreasonably withheld, other than an assignment by the Employer of any benefits of the Contract to the Bank or other financial institution which has provided finance for the construction and operation of the Project. On the enforcement of any security provided to the Bank or other financial institution, the Employer, any receiver of the Employer or any person having the benefit of such security or its nominee may assign any or all of rights under this Contract to any person.

Notwithstanding the foregoing, either Party may, upon written notice, assign and/or transfer the Contract to any third party in connection with any merger, reorganization, consolidation, operation of law or sale of all or substantially all of such Party’s business that is the subject of the Contract; provided that such third party, assignee or delegate has appropriate experience and expressly assumes in writing all of such Party’s duties and obligations hereunder.

  - Waiver of Contractual Rights

The waiver by any Party of any breach or default will not constitute a waiver of any different or subsequent breach or default or in any way to affect the validity of this Contract.

  - Warranties

For the Employer’s benefit, the Contractor shall obtain from the manufacturers or suppliers of the equipment, material, or services acquired in the context and for the purposes of the Works, the warranties against defects in materials and workmanship to the extent such warranties are reasonably obtainable, including those set out in Appendix B, and, the Contractor undertakes to take any steps and cover the relevant cost, as reasonably required for the maintenance of such warranties: The Contractor shall procure that such warranties are freely assignable to the Employer and the Bank or other lender of Employer in respect of the Project and shall assign all of its rights under such warranties to the Employer or the Bank or other lender of the Employer as may be directed by the Employer. In the event that any such assignment takes place before the expiry of the Defect Liability Warranty Period, the Contractor has the authority, during the Defect Liability Warranty Period, to act on behalf of the Employer in respect of all claims under or pursuant to the assigned warranties, in each case following prior notification and consultation with the Employer, it is clarified that the Contractor is under an obligation to act in accordance with all reasonable instructions of the Company given in that respect.

  - No change of control

The Contractor shall procure that there shall be no Change of Control in respect of the Contractor without the prior written consent of the Employer, such consent not to be unreasonably withheld.

For the purposes of this clause: “Control” means, in relation to a body corporate or partnership, the ability of a person or group of persons collectively to, directly or indirectly, direct that the affairs and business of the body corporate or partnership are conducted in accordance with the wishes of that person or group of persons:

- by means of the holding of shares and/or the possession of voting rights, in or in relation to that or any other body corporate or partnership;

- as a result of any powers conferred by the articles of association or any other document regulating that or any other body corporate or partnership; or

- otherwise.

A “Change of Control” occurs if a person who controls, or group of persons who collectively Control, anybody corporate or partnership ceases to do so or if another person, or group of persons collectively, acquires Control.

- Governing Law – Resolution of Disputes

This Contract with all its attachments shall be governed by the laws of Cyprus. A Party claiming that a dispute has arisen in relation to this Contract, shall notify the authorised representative of the other Party giving details of the dispute. If any dispute under this Contract remains unresolved for fifteen (15) business days from the date on which, a notice setting out the nature of the dispute is served by one Party on the other, either Party may request a meeting within a further five (5) business days between senior personnel (as notified by each Party to the other for this purpose), who shall have the power to resolve the dispute.

- All disputes arising out of or in connection with this Contract, including any question as with regards to its existence, validity or termination, shall be referred to and finally settled by arbitration under the Arbitration Law, Cap. 4. The number of arbitrators shall be one, the seat shall be in Nicosia and the language used in the arbitral proceedings shall be Greek.

- Force Majeure

If either Party is prevented or delayed from or in performing any of his obligations under the Contract due to circumstances beyond its reasonable control (Force Majeure), then it may notify the other Party about the circumstances constituting the Force Majeure and about the obligations or performance thereby being delayed or prevented, and the Party giving the notice shall thereupon be excused of such obligation for as long as the circumstances of prevention or delay may continue.

Force Majeure means:

- War hostilities (whether war be declared or not), invasion, act of foreign enemies,

- Ionizing radiations, or contamination by radioactivity from any nuclear fuel, or any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive or other hazardous properties of any explosive nuclear assembly or nuclear component thereof,

- Pressure waves caused by aircraft or other aerial devices traveling at sonic or supersonic speeds,

- Rebellion, revolution, insurrection, military power or civil war,

- Riot, terrorism, civil commotion or disorder,

- Embargo, blockage, legal prohibition, governmental action, labour strikes or lockouts

- Shortages, power outages,

- Earthquake, storm or similar natural disaster, fire, flood, epidemics

A Failure of the sub-contractors or suppliers of the Contractor to perform their respective duties and obligations shall under no circumstances constitute a Force Majeure unless such failure is attributed to a Force Majeure event under points 1 to 8.

It is stressed that the circumstances constituting the Force Majeure are accepted only as a delay factor and not as grounds for an indemnity or any other amendment to the terms and conditions of the Contract between the Parties. A failure or a delay in execution of the Contractor’s obligations to the Employer is not considered a circumstance constituting Force Majeure.

The Parties hereby agree that within 15 calendar days from the date of this Agreement, they (the Parties) will make any amendments to this Agreement and they will be bound by any amendments to this Agreement, as may be required by the Bank and its advisors, at the Bank’s discretion, as a condition for the provision by the Bank of financing to the Employer for the construction and operation of the Project.

In Witness whereof the parties have executed this Agreement through their duly authorized officers as of the date outlined in this Agreement.