GENERAL TERMS OF IMPLEMENTATION, SERVICE AND WARRANTY – PART II

1. Implementation Deadlines

1.1 The implementation begins after the Agreement is signed and the advance payment is received.

1.2 The standard project start time is 6–8 weeks from the date of signing the Agreement, unless otherwise agreed by the Parties.

1.3 The final completion date will be confirmed after verifying the full technical and electrical readiness on the Customer’s side.

1.4 Full readiness includes in particular:

a) Delivery of complete technical documentation of the installation (PV, BESS, EV, generators, switchgear, metering).
b) Completion of all electrical works, including wiring, connections, device installation and initial configuration.
c) Completion and acceptance of the grid connection.
d) Energization of the facility and commissioning of devices in accordance with the technical documentation.
e) Ensuring full operability of the devices and their correct response to EMS/SCADA control commands.
f) Agreement with the DSO/TSO on the scope of signals, functionalities and control logic.
g) Proper operation of the telecommunications infrastructure, including:

• access to LAN/WAN,
• dedicated VLANs,
• remote access (VPN), if required,
• static IP addressing of devices,
• local and remote access,
• protection measurements and acceptance tests.

h) Configuration of IP addressing for all devices communicating with EMS/SCADA.
i) Ensuring stable power supply and correct network parameters.
j) Appointment of a coordinator on the Customer’s side.
k) Provision of local or remote access for the Contractor to devices and communication networks.
l) Completion of all technical acceptance procedures required by law.

1.5 Any delay resulting from the failure to meet the above conditions extends the implementation schedule without consequences for the Contractor.

1.6 The Contractor undertakes to deliver and implement the EMS/SCADA system within up to 28 days from the moment the Customer meets all readiness conditions.

1.7 Commissioning and acceptance tests shall be carried out within 14 days from confirming the readiness of the installation.

2. Scope and Method of Implementation

2.1 The Contractor implements the EMS/SCADA system in accordance with the functional scope defined in the Agreement.

2.2 Programming, configuration and commissioning works are performed remotely unless otherwise agreed by the Parties.

2.3 On-site works are carried out in accordance with the schedule and scope defined in Part I – Functional, Technical and Commercial Scope.

2.4 The scope of work is based on documentation provided by the Customer and may be clarified after preparing execution documentation and verifying the actual condition of the installation.

2.5 The Customer undertakes to:

a) Provide the necessary technical infrastructure.
b) Deliver documentation and configuration data.
c) Provide remote access to the site's network infrastructure.
d) Appoint a person responsible for coordination.

2.6 If discrepancies arise between documentation and the actual installation, the Parties will adjust the work scope, deadlines and costs accordingly.

3. On-site Works

3.1 On-site works include:

• the first technical visit,
• system integration and commissioning,
• personnel training.

3.2 The number of on-site workdays is defined individually in the Agreement.

3.3 Visit dates are scheduled at least 14 days in advance and only after meeting all readiness conditions.

3.4 Changes in the number of on-site days require mutual agreement and may affect the cost of implementation.

3.5 Travel, accommodation and delegation expenses are billed separately.

4. Exclusions from the Agreement

4.1 The Agreement does not include, in particular:

a) additional installation works,
b) additional configuration or re-commissioning of the Customer’s devices,
c) integrations with external systems not included in the Agreement,
d) on-site works other than those defined in Part I – Functional, Technical and Commercial Scope,
e) configuration of communication devices, inverters, protection relays,
f) works related to the SCADA system of the distribution operator (DSO).

4.2 The implementation cost may change depending on the actual configuration of devices.

4.3 The Customer is obliged to provide all data and access required to begin the works.

4.4 Additional requirements outside the Agreement will be priced individually.

4.5 Failure to perform the works due to reasons attributable to the Customer does not release them from the obligation to pay.

4.6 The system is installed in accordance with communication standards and manufacturer requirements.

5. Subscription and Technical Support

5.1. Subscription Scope

The subscription includes:

• System updates and functional development.
• Cybersecurity maintenance (certificates, access policies, ISO 27001 / NIS2 compliance).
• Database administration and backup.
• Maintenance of integration protocols (Modbus, MQTT, TCP/IP, etc.).
• Access to advanced EMS modes (arbitrage, Peak Shaving, Zero/Set import/export).
• Access to external data (energy prices, forecasts, operator signals).
• Service and operational support.
• Multi-site management.

5.2. Subscription Period and Billing Models

5.2.1 Available periods: 1–10 years.

5.2.2 Billing models:

• monthly,
• annual upfront,
• one-time payment for the entire period.

5.2.3 After the subscription expires:

a) All service, updates and integration functions expire.
b) The system operates solely as a local EMS, without access to:

• SCADA,
• cloud and synchronization,
• historical data stored by the Contractor,
• external data sources.

5.3. Technical Support

5.3.1 Basic subscription support includes up to 1 hour per month.

5.3.2 Support scope includes:

• remote access connections,
• log analysis,
• error diagnostics,
• operational consultations.

5.3.3 Unused support time does not carry over to subsequent months.

5.3.4 Work exceeding the limit is billed according to the current price list.

5.3.5 Support does not cover issues caused by:

a) the Customer’s infrastructure (LAN/WAN/VPN/IP),
b) malfunction of external devices (inverters, BESS, EV chargers, meters),
c) third-party interference,
d) failure to meet the technical requirements of the Agreement.

6. Acceptance of Works

6.1 System acceptance is confirmed by a protocol signed by both Parties.

6.2 Comments to the protocol may be submitted within 7 days from receiving the test results.

7. Warranty

7.1 The warranty covers:

a) removal of critical errors,
b) corrections resulting from the Contractor’s fault,
c) ensuring software stability,
d) repair or replacement of defective hardware supplied by the Contractor.

7.2 Service response time is up to 36 working hours.

7.3 Warranty may be extended for: 1 / 3 / 5 / 10 years.

7.4 Warranty extension requires:

• an active subscription,
• the system updated to the latest available version.

7.5 The warranty does not cover:

a) third-party interference,
b) improper operation,
c) failures of external devices,
d) communication issues on the Customer’s side.

8. Liability of the Parties

8.1 The Contractor is responsible for implementing the system in accordance with the Agreement.
8.2 The Customer is responsible for data accuracy and operation of the technical infrastructure.

9. Confidentiality

The Parties undertake to maintain confidentiality of all technical and commercial information.

10. Final Provisions

10.1 Any amendments to the Agreement require written form.

10.2 For matters not regulated herein, the provisions of the Polish Civil Code apply.

10.3 The Agreement is executed in two identical copies — one for each Party.

11. Relationship of Documents

Part II constitutes an integral part of the Agreement and shall be applied in accordance with the rules defined in Part I.