SOLAR PHOTOVOLTAIC SYSTEM COMMISSIONING CONTRACT

Lighthief Cyprus Ltd · Procurement and Delivery Contractor

# PARTIES

## Contractor

| Company | LIGHTHIEF CYPRUS LTD |
| --- | --- |
| Reg. No. | HE 477423 |
| TIN | 60187188Q |
| Address | 28 October Ave 249, Lophitis Business Center 1, Office 201, 3035 Limassol, Cyprus |
| Email | office@lighthief.com |
| Tel | +357 77 77 00 50 |
| Representative | Alexander Papacosta |

## Client

| Full Name / Company | [Fill] |
| --- | --- |
| ID / Reg. No. | [Fill] |
| Address | [Fill] |
| Email | [Fill] |
| Tel | [Fill] |
| Representative | [Fill] |

# RECITALS

WHEREAS the Client wishes to install a photovoltaic solar system at the Property Address

specified above; and

WHEREAS the Contractor is duly licensed and qualified to design, supply, install, and commission photovoltaic systems in accordance with Cyprus law and regulations;

NOW THEREFORE, in consideration of the mutual covenants and agreements contained herein, the parties agree as follows:

# 1. SCOPE OF WORK

## 1.1 System Specifications

The Contractor shall supply, deliver, install, and commission a photovoltaic and battery energy storage system (where batteries are applicable) at the premises specified below. The scope includes all labour, materials, cabling, protection devices, and programming required for a fully operational photovoltaic system.

| Parameter | Specification |
| --- | --- |
| Installation Address | [Address] |
| Solar Panels | [No. of Panels] x [Panel Power W] [Model] |
| PV Capacity (kWp) | [PV total capacity kW] |
| Inverter(s) (kW) | [No. of Inverters] x [Inverter kW] [Model] |
| Battery Unit(s) | [No. of BESS] x [BESS Capacity kWh] [Model] |
| Battery Capacity (kWh) | [Battery total capacity kWh] |
| Generator Interface | □ ATS included □ Not included |
| Monitoring | □ Included □ Not included |

## 1.2 Services Included

The Contractor shall provide:

- Site assessment and system design,

- Submission of application to EAC (Electricity Authority of Cyprus),

- Handling of all necessary permits and approvals,

- Supply of all equipment and materials,

- Professional installation in accordance with Cyprus standards,

- System commissioning and testing,

- Assistance to the client with any available government subsidy applications,

- Training on system operation and monitoring.

## 1.3 Installation Standards

All work shall comply with:

- Cyprus Electricity Authority (EAC) regulations,

- Cyprus Energy Regulatory Authority (CERA) requirements,

- EU safety and quality standards,

- Local building and planning regulations,

- All applicable Cyprus laws and regulations.

# 2. TIMELINE AND MILESTONES

## 2.1 Project Timeline

- Contract Signing Date: [Date] [Month] [Year],

- EAC Application Submission: 1-2 weeks after all the documents have been provided by the customer,

- Expected EAC Approval: 5-8 weeks from application submission (Depending on EAC),

- Installation of Solar Panels: Within 4 months from contract signing,

- Installation Duration: 2-3 working days,

- EAC Inspection: As scheduled by EAC,

- System Commissioning: Upon successful EAC inspection.

## 2.2 Delays

The Contractor shall not be liable for delays caused by:

- EAC processing times,

- Weather conditions,

- Force majeure events,

- Client-requested changes,

- Delays in obtaining permits beyond Contractor's control.

# 3. PAYMENT TERMS

## 3.1 Total Contract Price

| Total Contract Price (VAT incl. 19%) | € [Price] |
| --- | --- |
| Net Amount (excl. VAT) | € [Price] |
| VAT (19%) | € [Price] |

## 3.2 Payment Schedule

Payments shall be made by bank transfer to the Contractor's account. No works shall commence or materials ordered until the deposit (Instalment 1) is received.

| Instalment | Trigger |
| --- | --- |
| #1 — Deposit (40%) | Due upon contract signing |
| #2 — Pre-Installation (55%) | Due 3 days before installation date |
| #3 — Final (5%) | Upon approval for grid connection by EAC |

All amounts are VAT-inclusive. Late payments accrue interest at 2% per month on the outstanding balance.

Not included to the above contractor payments: DSO (EAC) one-time application (covers the DSO’s processing cost, the inspection, and connection of the system to the distribution network (connection terms), and the ripple control system (connection of remote control). DSO application fee: approximately €365 + VAT (19%) = €434.35, payable directly to DSO upon issuance of connection terms.

## 3.3 Government Subsidies

The Contractor will assist in applying for available subsidies.

Subsidies will be paid directly to the Client by the authorities.

# 4. WARRANTIES AND GUARANTEES

## 4.1 Equipment Warranties

| Item | Coverage |
| --- | --- |
| Workmanship | 1 year from commissioning date |
| PV Modules | As per OEM — [input warranties] |
| Inverter | As per OEM — [input warranties] |
| Battery Modules | As per OEM — [input warranties] |

Warranties are void if: (a) the system is modified without the Contractor's consent; (b) damage is caused by Client negligence, misuse, or acts of God; (c) payment obligations are not fulfilled.

*OEM – Original Equipment Manufacturer.

## 4.2 Legal Guarantee

In accordance with Cyprus Law 154(I)/2021, the Client is entitled to a minimum two-year legal guarantee from the date of delivery of the equipment, covering any lack of conformity of the goods. Installation works and services are covered separately under the terms of this agreement.

# 5. CLIENT OBLIGATIONS

The Client shall:

- Provide accurate electricity consumption data (last 6 bills),

- Ensure clear access to the installation site,

- Obtain consent from co-owners (if applicable),

- Provide necessary documentation for EAC application,

- Make payments according to the agreed schedule,

- Not modify the system without Contractor approval,

  - If the main distribution board needs to be extended and any inverter shading fall under the client’s responsibility, however we can provide advice for this.

# 6. CONTRACTOR OBLIGATIONS

The Contractor shall:

- Perform all work with professional competence,

- Use only certified, high-quality equipment,

- Comply with all safety regulations,

- Obtain all necessary permits and approvals,

- Provide proper documentation and certificates,

- Train the Client on system operation,

- Respond to warranty claims within reasonable time.

# 7.  MAINTENANCE AND SUPPORT

## 7.1 Maintenance Services

The Contractor offers optional maintenance packages:

- Annual inspection and cleaning,

- Performance monitoring and reporting,

- Priority response for service calls.

## 7.2 Client Maintenance

The Client should:

- Keep panels reasonably clean,

- Monitor system performance,

- Report any issues promptly,

- Not obstruct panels with new structures.

# 8. NET BILLING TERMS

## 8.1 EAC Contract

The Client will enter into a Net Billing contract with EAC for:

- Residential: as per current EAC/CERA Net Billing framework,

- Commercial: as per current EAC/CERA Net Billing framework.

Under Net Billing, electricity produced by the photovoltaic system is first consumed on-site. At the end of the two-month billing period, all imported and exported energy is offset at the same price. Any surplus exported energy is credited at the export tariff set by EAC/CERA, and any electricity imported from the grid is charged at the applicable retail tariff.

## 8.2 Tariffs and Settlement

- After the end of a billing period all imported and exported energy is offset at the same price,

- Imported electricity is charged at the standard retail tariff applicable to the Client’s supply category,

- Surplus exported electricity is credited at the official Net Billing export tariff set by EAC/CERA,

- Imported and exported electricity are valued separately at different tariffs.

## 8.3 Credit Handling

- Export credits are applied against import charges in the Client’s EAC bill,

- Credits are not paid out in cash unless explicitly allowed by EAC regulations in force at the time.

## 8.4 Fees

The Client shall pay all standard EAC charges applicable under Net Billing, including:

- Supply charges,

- Network charges,

- Ancillary service charges,

- Any Net Billing–specific administrative or settlement fees, as determined by EAC/CERA and subject to future regulatory changes.

# 9. INSURANCE AND LIABILITY

## 9.1 Contractor Insurance

The Contractor maintains:

- Professional liability insurance,

- Public liability insurance,

- Workers' compensation insurance.

## 9.2 Limitation of Liability

Except for gross negligence or willful misconduct, the Contractor's liability shall not exceed the total contract value.

## 9.3 Indemnification

Each party shall indemnify the other against claims arising from their own negligence.

# 10. TERMINATION AND CANCELLATION

## 10.1 Client Cancellation Rights

Under the EU Consumer Rights Directive (2011/83/EU), where applicable to distance or off-premises contracts, the Client has 14 days to cancel without penalty.

## 10.2 Cancellation After Commencement

- Upon signing the contract: 10% cancellation fee,

- After the EAC application submission: 30% cancellation fee,

- After system installation: No refund.

## 10.3 Contractor Termination

The Contractor may terminate for:

- Non-payment after 30 days written notice,

- Client breach of obligations,

- Discovery of unsafe conditions.

# 11. DISPUTE RESOLUTION

## 11.1 Amicable Resolution

The Client may contact the Cyprus Consumer Protection Service for assistance.

## 11.3 Legal Proceedings

Any unresolved disputes shall be subject to the exclusive jurisdiction of Cyprus courts.

# 12. DATA PROTECTION

The Contractor shall comply with GDPR and Cyprus data protection laws regarding any personal data collected.

# 13. GENERAL PROVISIONS

## 13.1 Entire Agreement

This Contract constitutes the entire agreement between the parties.

## 13.2 Amendments

Any amendments must be in writing and signed by both parties.

## 13.3 Governing Law

This Contract is governed by the laws of the Republic of Cyprus.

## 13.4 Language

This Agreement is executed in the English language, which shall be the governing language.

## 13.5 Severability

If any provision is deemed invalid, the remainder shall continue in effect.

## 13.6 Force Majeure

Neither party shall be liable for delays due to circumstances beyond their reasonable control.

# 14. SPECIAL CONDITIONS

Lighthief Cyprus Ltd guarantees to replace tiles if any broken with tiles of same style, or any kind of damage during the installation.

# SIGNATURES

By signing below, both parties confirm they have read, understood, and agreed to all terms of this Contract.

| FOR THE CLIENT | FOR THE CONTRACTOR — LIGHTHIEF CYPRUS LTD |
| --- | --- |
| Name: | Name: Alexander Papacosta |
| Capacity: | Capacity: Director |
| Signature: | Signature: |
| Date: | Date: |

* Each Party shall retain one signed original of this contract.

# IMPORTANT NOTICE TO CLIENT

This contract includes important terms regarding your rights and obligations.

You are advised to:

- Read all terms carefully before signing,

- Keep a copy for your records,

- Understand the payment schedule,

- Note the warranty periods,

- Be aware of your consumer rights under Cyprus law.

For more information on consumer rights, contact:

- Cyprus Consumer Protection Service: 1429,

- Cyprus Energy Regulatory Authority (CERA): +357 22 666 363.

# Payment – Bank Details

| Account name: | LIGHTHIEF CYPRUS LTD |
| --- | --- |
| Account Number: | 357044102353 |
| IBAN: | CY86002001950000357044102353 |
| SWIFT/BIC: | BCYPCY2N |
| Bank Name: | Bank of Cyprus |