Galascope Lawyer comments

1. The EPC must be conditional on signing of the LTSA. Several EPC protections only work if the LTSA is in place: the warranty void carve out for monitoring failures, the on site labour that fills the gap in the OEM's parts only remedy, and the availability guarantee itself. The EPC should therefore include execution of the LTSA as a condition precedent (alongside the existing conditions in Annex 1A.5), or at minimum a simultaneous execution requirement, so that Galascope is never bound to the EPC without the LTSA protections attached.

2. The OEM performance guarantee is weaker than it appears. It is a corporate promise from Linyang, not a bank guarantee (clause 3 says so expressly), it is governed by Chinese law with Shanghai arbitration (clause 11), it requires 30 days' notice and cure before we can demand (clause 7), and it expires at the end of the defects liability period, i.e. only 3 months after PAC (clause 6). It also expressly confirms no parent company guarantee is provided (clause 8). It is real but modest protection.

Ask: extend validity to at least 12 months post PAC, and reduce the cure period for insolvency type events (partly there already).

3. Defects liability period - renew the 6 month ask. Still 3 months (EPC Section 9.2). This matters more now because both the 5% retention and the OEM performance guarantee expire with it. Moving the DLP to 6 months extends three protections at once. This is our ask.

4. LTSA (structural point, noted now) - downtime caused by the EMS does not count against the availability guarantee (LTSA Section 9.3(e)). Normally a fair exclusion for third party software. But here the EMS provider (DISPERON) is an affiliate of the same group as the Service Provider. As drafted, their own group company can cause an outage and the 97% guarantee is not engaged.

Ask: the exclusion should not apply where the EMS failure is attributable to DISPERON or any Lighthief group entity.

5. Technical Agreements - two inconsistencies to fix. (i) The warranty void thresholds differ from the EPC: the Technical Agreement voids the battery warranty at cell voltage 2.7V or below for 120 hours, and requires charging every 3 months and storage of no more than 6 months from factory. If Connection Terms or commissioning are delayed, someone must be contractually responsible for the interim charging and storage - pre PAC this must sit with Lighthief, and it should be stated. (ii) The Technical Agreement says the EMS is provided by the customer, which contradicts the DISPERON structure. Both are drafting fixes, but the storage and charging point has real money behind it if commissioning slips.

6. Grid forming - capture the price position in writing. The cover materials say activating grid forming (VSG) later is expected at no price change, but the Technical Agreement says any grid forming requirements beyond the stated German standard are subject to price recalculation. These two statements will collide later. One line in the EPC or Technical Agreement fixing that VSG and black start activation on the supplied hardware is at no additional equipment cost would close it.

7. Bank guarantees - confirm the two open items. The specimen guarantees are genuinely strong: first demand, URDG 758, Galascope named directly as beneficiary, payment in 5 days without set off, valid to PAC, assignable to lenders. Two things are left open in the specimens: the identity of the issuing bank and the governing law, both marked to be confirmed.

Our position: issuing bank must be acceptable to us (or confirmed through a Cyprus/EU bank), and final instruments must match the specimen wording. This is execution discipline rather than negotiation.

B. Risks to be aware of

The following are risks which the board should take its decision aware of them.

-    Manufacturing defect protection ultimately rests on Lighthief's covenant. The DWU does now disapply the OEM's 10% cap for confirmed manufacturing defects (DWU 5.3). But the OEM decides in the first instance whether a defect is a manufacturing defect (DWU 3.3), and enforcing the DWU means Chinese law arbitration in Shanghai. Our practical protection is Lighthief's uncapped Cyprus law liability under the EPC, which is only as strong as Lighthief's balance sheet - and the performance guarantee expressly notes no parent guarantee is given. If the board wishes to strengthen this, a parent guarantee from Lighthief International would do more than any drafting change. Otherwise this is a risk to be taken with eyes open.

-    Availability protection is thin. The 97% guarantee is measured across both parks combined (LTSA 9.2A), so one park can be down for weeks without breach if the other performs. The LDs are a percentage of the annual service fee, capped at 20% of it (roughly EUR 13,000 a year on Tier C), and are the sole remedy (LTSA 9.4 to 9.6). This is compensation for service failure, not for lost revenue. The board must understand that the 97% figure does not constitute revenue protection.

-    LTSA liability cap and exit. Service Provider liability is capped at 12 months of fees (LTSA 14.2) and either party can terminate for convenience on 180 days' notice (LTSA 13.4). If Lighthief exits, the availability guarantee goes with them.

Before signature - checklist

-    DWU and performance guarantee signed and sealed by Linyang (both are still drafts).

-    Final bank guarantees issued matching the specimens, from an acceptable bank, governing law confirmed.

-    EMS Addendum executed; Lighthief Cyprus guarantee confirmed to cover it.

-    Technical Agreement fixes in A.4 and the grid forming line in A.5.

-    LTSA executed simultaneously with (or as a condition of) the EPC, its Schedule 2 completed (tier selection and figures are currently blank) and its reference updated from EPC v4.0 to v6.